# PMP FLASHCARDS

By Kimberly Wiethoff, MBA, PMP,  PMI-ACP

## ✅ DOMAIN I: PEOPLE (42%)

### Section 1: Build a Team

FLASHCARD 1

Front: What is the purpose of a Team Charter?
Back: Defines roles, responsibilities, decision authority, and team norms.
Memory Hook: If team confusion exists → Build/update Team Charter.

FLASHCARD 2

Front: What tool defines roles and responsibilities?
Back: RACI Matrix (Responsible, Accountable, Consulted, Informed)
Memory Hook: If anyone says “Who owns this?” → Think RACI.

FLASHCARD 3

Front: What model describes team formation stages?
Back: Tuckman’s Model — Forming, Storming, Norming, Performing, Adjourning
Memory Hook: Storming = conflict → guide to Norming.

### Section 2: Lead a Team

FLASHCARD 4

Front: What is Servant Leadership?
Back: Leading by supporting team needs, removing blockers, coaching, enabling.
Memory Hook: Team empowerment + removing obstacles.

FLASHCARD 5

Front: Which leadership style fits Agile environments?
Back: Servant and facilitative leadership.
Memory Hook: Agile = empower, not command.

FLASHCARD 6

Front: How should a PM address team conflict?
Back: Facilitate direct collaboration between involved parties.
Memory Hook: PMI loves “collaborate” first.

### Section 3: Support Team Performance

FLASHCARD 7

Front: What is the PM’s responsibility when a team member underperforms?
Back: Coach the team member privately, identify root cause, support improvement.
Memory Hook: Coach → Don’t punish first.

FLASHCARD 8

Front: What technique helps improve performance?
Back: Frequent feedback loops and regular performance check-ins.
Memory Hook: Feedback early → fewer escalations.

### Section 4: Empower Team Members and Stakeholders

FLASHCARD 9

Front: What should PM do when approvals create bottlenecks?
Back: Empower team decision-making within limits defined by governance.
Memory Hook: Bottleneck → distribute authority.

FLASHCARD 10

Front: Power types in project management?
Back: Legitimate, Reward, Expert, Referent, Coercive
Memory Hook: Expert + Referent are PMI-preferred.

### Section 5: Ensure Training and Competency

FLASHCARD 11

Front: What to do when a skill gap is found?
Back: Create and execute a training plan.
Memory Hook: Gap → Train → THEN escalate.

### Section 6: Build Shared Understanding

FLASHCARD 12

Front: Which techniques promote shared understanding?
Back: Workshops, JAD sessions, prototypes, demos.
Memory Hook: Miscommunication → Facilitate, don’t dictate.

### Section 7: Manage Conflict

FLASHCARD 13

Front: List conflict resolution styles (best to worst).
Back: Collaborate → Compromise → Smooth → Force → Withdraw
Memory Hook: PMI = ALWAYS collaborate unless emergency.

## ✅DOMAIN II: PROCESS (50%)

### Section 8: Execute Project with Urgency

FLASHCARD 14

Front: What does “deliver business value” imply?
Back: Remove impediments, accelerate flow, focus on MVP.
Memory Hook: Value = unblock + deliver early.

### Section 9: Manage Communications

FLASHCARD 15

Front: Types of communication?
Back: Push, Pull, Interactive
Memory Hook: Stakeholder misalignment → review communication plan.

FLASHCARD 16

Front: What’s the first step when stakeholders are unhappy?
Back: Engage and listen to concerns directly.
Memory Hook: Talk → Align → Update plan.

### Section 10: Assess & Manage Risks

FLASHCARD 17

Front: Negative risk responses?
Back: Avoid, Mitigate, Transfer, Accept
Memory Hook: AMTA.

FLASHCARD 18

Front: Positive risk responses?
Back: Exploit, Enhance, Share, Accept
Memory Hook: EESA.

FLASHCARD 19

Front: What to do when a new risk emerges?
Back: Add to risk register → Assess probability & impact → Develop response.
Memory Hook: Always ANALYZE before acting.

### Section 11: Engage Stakeholders

FLASHCARD 20

Front: First action for new stakeholders?
Back: Add to stakeholder register and analyze influence.
Memory Hook: New person → Update the register FIRST.

### Section 12: Plan & Manage Scope

FLASHCARD 21

Front: How is WBS created?
Back: By decomposition of deliverables.
Memory Hook: WBS = What not how.

FLASHCARD 22

Front: What is scope creep?
Back: Uncontrolled/unauthorized changes.
Memory Hook: Creep = no change control used.

### Section 13: Plan & Manage Schedule

FLASHCARD 23

Front: What is the critical path?
Back: Longest path; determines minimum project duration.
Memory Hook: No float = critical.

FLASHCARD 24

Front: What’s the formula for float?
Back: LS – ES or LF – EF
Memory Hook: Slack = Late – Early.

### Section 14: Budget & Cost

FLASHCARD 25

Front: CPI < 1 means what?
Back: Cost overrun; project is less efficient than planned.
Memory Hook: CPI < 1 = Losing money.

FLASHCARD 26

Front: SPI < 1 means what?
Back: Behind schedule.
Memory Hook: SPI < 1 = Behind.

### Section 15: Manage Quality

FLASHCARD 27

Front: What’s the difference between QA and QC?
Back: QA = process-oriented; QC = product-oriented
Memory Hook: A = Audit; C = Check.

FLASHCARD 28

Front: What tool identifies defect causes?
Back: Ishikawa / Fishbone diagram
Memory Hook: Fishbone = root cause.

### Section 16: Integration Planning

FLASHCARD 29

Front: What is the purpose of the Project Management Plan?
Back: Centralized document integrating all subsidiary plans.
Memory Hook: Master document = integration.

### Section 17: Manage Change

FLASHCARD 30

Front: Steps in change control (in order)?
Back: Document → Analyze → CCB → Update plans → Communicate
Memory Hook: NEVER skip analysis.

### Section 18: Procurement

FLASHCARD 31

Front: Fixed-price contracts transfer risk to whom?
Back: The seller.
Memory Hook: FP = seller risk.

FLASHCARD 32

Front: What is a make-or-buy analysis used for?
Back: Determining whether to produce internally or outsource.
Memory Hook: Buy = cost/time; Make = control.

## ✅ DOMAIN III: BUSINESS ENVIRONMENT (8%)

### Section 21: Compliance

FLASHCARD 33

Front: What to do if regulatory requirement discovered late?
Back: Update compliance plan and escalate risk.
Memory Hook: Compliance = no negotiation.

### Section 22: Deliver Benefits & Value

FLASHCARD 34

Front: What is the Benefits Management Plan?
Back: Defines how benefits are measured, tracked, and realized.
Memory Hook: Benefits = business justification.

FLASHCARD 35

Front: What if benefits are not materializing?
Back: Reassess business case and realign project goals.
Memory Hook: No benefit = reconsider.

### Section 23: Organizational Change

FLASHCARD 36

Front: What model explains individual change adoption?
Back: ADKAR: Awareness, Desire, Knowledge, Ability, Reinforcement
Memory Hook: A-D-K-A-R.

FLASHCARD 37

Front: How handle resistance to change?
Back: Increase communication, involvement, and support.
Memory Hook: Resistance = engage more, not less.

## DOMAIN I : People

### 📘 SECTION 1: BUILD A TEAM — COMPLETE FLASHCARD SET

✅ FLASHCARD 1

Front: What is the Team Charter?
Back: A document that defines team values, working agreements, roles, responsibilities, decision-making, and communication norms.
Memory Hook: If team confusion → Build/update Team Charter.
Trigger Words: “unclear expectations,” “misalignment,” “team norms missing”

✅ FLASHCARD 2

Front: When is the Team Charter created?
Back: During project initiation and refined throughout planning.
Memory Hook: Start early → refine later.
Trigger Words: “establishing team norms early,” “kickoff preparation”

✅ FLASHCARD 3

Front: What process outputs the Team Charter?
Back: Develop Team Charter is part of Resource Management planning.
Memory Hook: Charter = resource planning output.
Trigger Words: “team formation,” “roles/responsibilities needed”

✅ FLASHCARD 4

Front: What is the purpose of RACI Matrix?
Back: Defines who is Responsible, Accountable, Consulted, and Informed for each task.
Memory Hook: If ownership unclear → think RACI.
Trigger Words: “who is responsible,” “duplicate work,” “handoff problems”

✅ FLASHCARD 5

Front: What is the difference between roles and responsibilities?
Back: Roles = position/title; Responsibilities = specific duties/actions.
Memory Hook: Role = what you ARE; Responsibility = what you DO.
Trigger Words: “job title vs tasks,” “clarifying duties”

✅ FLASHCARD 6

Front: What is Tuckman’s Ladder?
Back: Team development stages: Forming, Storming, Norming, Performing, Adjourning.
Memory Hook: Storming = conflict; Performing = independence.
Trigger Words: “team in conflict,” “new team forming”

✅ FLASHCARD 7

Front: How should the PM respond during Storming phase?
Back: Facilitate healthy conflict, mediate disagreements, reinforce team norms.
Memory Hook: Storming → guide to Norming.
Trigger Words: “team arguing,” “conflict arises naturally”

✅ FLASHCARD 8

Front: What is the responsibility assignment matrix (RAM)?
Back: A chart linking work packages to team members.
Memory Hook: RAM = visual assignment chart.
Trigger Words: “work package ownership,” “team accountability”

✅ FLASHCARD 9

Front: What is the purpose of Organizational Theory?
Back: Helps PM understand behavior, structure, culture → builds better teams.
Memory Hook: Know the org → build the team.
Trigger Words: “organizational culture,” “team behavior,” “structure impact”

✅ FLASHCARD 10

Front: What are Resource Requirements?
Back: Identified quantities and types of human and physical resources needed.
Memory Hook: Requirements first → assignments later.
Trigger Words: “resource constraints,” “skills needed,” “capacity planning”

✅ FLASHCARD 11

Front: What is Resource Breakdown Structure (RBS)?
Back: Hierarchical listing of resources by category and type.
Memory Hook: RBS = resource categories → not tasks.
Trigger Words: “resource categories,” “classification”

✅ FLASHCARD 12

Front: What is the difference between Acquire Team vs Develop Team?
Back: Acquire = bring people onto the project; Develop = improve their skills/performance.
Memory Hook: Acquire = get people; Develop = grow people.
Trigger Words: “new resources needed,” “team training,” “skill improvement”

✅ FLASHCARD 13

Front: What are Acquisition Constraints?
Back: Limitations such as budget, org policies, availability, location.
Memory Hook: Constraints dictate options.
Trigger Words: “resource shortages,” “staffing limitations,” “policy restrictions”

✅ FLASHCARD 14

Front: What should PM do when the team lacks required skills?
Back: Provide training, mentoring, or acquire external resources.
Memory Hook: Skill gap → training plan BEFORE escalation.
Trigger Words: “insufficient skills,” “team not qualified”

✅ FLASHCARD 15

Front: What is the best method to establish team values?
Back: Facilitation workshops involving the entire team.
Memory Hook: Build values collaboratively.
Trigger Words: “team agreement,” “shared values,” “kickoff activity”

✅ FLASHCARD 16

Front: What is the Halo Effect?
Back: Incorrectly assuming a good performer in one area will be good at everything.
Memory Hook: Halo ≠ all skills.
Trigger Words: “promotion error,” “assign based on assumptions”

✅ FLASHCARD 17

Front: What is multi-criteria decision analysis used for?
Back: Evaluates resource alternatives based on weighted criteria (skills, cost, availability).
Memory Hook: Pick best resource objectively.
Trigger Words: “choose team members,” “select vendor,” “compare options”

✅ FLASHCARD 18

Front: What is pre-assignment?
Back: When staff is chosen in advance due to skill, availability, or customer request.
Memory Hook: Pre-assigned = locked in before planning.
Trigger Words: “customer mandates,” “contract requirement,” “named resources”

✅ FLASHCARD 19

Front: What is virtual team formation?
Back: Teams working remotely across locations, cultures, or time zones.
Memory Hook: Virtual = communication planning is critical.
Trigger Words: “remote team,” “time zone,” “distributed resources”

✅ FLASHCARD 20

Front: What tools help support virtual teams?
Back: Video conferencing, collaboration tools, shared repositories.
Memory Hook: Tools replace face-to-face.
Trigger Words: “communication challenges,” “remote collaboration”

✅ FLASHCARD 21

Front: Why is diversity important in team building?
Back: Increases creativity, problem solving, and innovation.
Memory Hook: Diverse teams → better results.
Trigger Words: “mixed backgrounds,” “inclusive team,” “global team”

✅ FLASHCARD 22

Front: What is resource smoothing?
Back: Adjusts activities so resource usage remains within limits without affecting critical path.
Memory Hook: Smoothing = no impact to critical path.
Trigger Words: “minor leveling,” “optimize usage”

✅ FLASHCARD 23

Front: What is resource leveling?
Back: Adjusts schedule to address resource conflicts, often extending duration.
Memory Hook: Leveling impacts schedule.
Trigger Words: “overallocation,” “schedule adjustment,” “dependency conflict”

✅ FLASHCARD 24

Front: What is a responsibility assignment matrix used for in team building?
Back: Prevents overlap, confusion, and finger-pointing by clarifying ownership.
Memory Hook: RACI = clarity + accountability.
Trigger Words: “duplication,” “blame,” “handoff issues”

✅ FLASHCARD 25

Front: What should PM do when team members do not agree on roles?
Back: Facilitate a discussion to co-create the Team Charter.
Memory Hook: PMI always prefers collaboration.
Trigger Words: “role disputes,” “misalignment,” “confusion about responsibilities”

### 📘 SECTION 2: LEAD A TEAM

✅ FLASHCARD 1

Front: What is the primary leadership approach recommended by PMI?
Back: Servant Leadership—empower, support, remove blockers, coach.
Memory Hook: Team-first → Servant Leader.
Trigger Words: “help team succeed,” “remove obstacles,” “empower team”

✅ FLASHCARD 2

Front: What leadership style works best in Agile teams?
Back: Servant and Facilitative leadership.
Memory Hook: Agile = empower, don’t command.
Trigger Words: “self-organizing team,” “collaborative environment”

✅ FLASHCARD 3

Front: What is Emotional Intelligence (EI)?
Back: Understanding and managing personal emotions and others’ emotions to enhance communication and collaboration.
Memory Hook: EI = empathy + awareness.
Trigger Words: “empathy,” “self-awareness,” “relationship management”

✅ FLASHCARD 4

Front: What is the PM’s role in conflict management?
Back: Facilitate resolution, promote collaboration, ensure constructive communication.
Memory Hook: PMI → Always collaborate first.
Trigger Words: “team conflict,” “disagreements,” “facilitated session”

✅ FLASHCARD 5

Front: What leadership action is needed when a team member is not participating?
Back: Engage privately, ask questions, encourage involvement, uncover blockers.
Memory Hook: Silence = check in one-on-one.
Trigger Words: “quiet team member,” “withdrawal,” “lack of engagement”

✅ FLASHCARD 6

Front: How does a PM motivate team members?
Back: Recognize achievements, empower ownership, connect to purpose, provide autonomy.
Memory Hook: Motivation = autonomy + recognition.
Trigger Words: “low morale,” “motivation issues,” “reduced productivity”

✅ FLASHCARD 7

Front: What is the best conflict resolution style?
Back: Collaboration (win-win) unless urgent or safety-critical.
Memory Hook: PMI answers = collaboration first.
Trigger Words: “win-win,” “consensus,” “root cause discussion”

✅ FLASHCARD 8

Front: What is the worst conflict management style for long-term results?
Back: Forcing (win-lose).
Memory Hook: Force = conflict returns later.
Trigger Words: “imposed decision,” “authority-based,” “commanding style”

✅ FLASHCARD 9

Front: When is forcing acceptable?
Back: Emergencies, safety issues, severe conflict threatening project goals.
Memory Hook: Only use Force in emergencies.
Trigger Words: “urgent decision,” “critical risk,” “time-sensitive escalation”

✅ FLASHCARD 10

Front: What is smoothing in conflict management?
Back: Downplaying differences and emphasizing agreement.
Memory Hook: Smoothing = temporary peace.
Trigger Words: “calm situation,” “buy time,” “avoid escalation”

✅ FLASHCARD 11

Front: What is compromising?
Back: Each party gives something up to reach agreement—short-term solution.
Memory Hook: Compromise = partial win.
Trigger Words: “middle ground,” “agreement needed quickly”

✅ FLASHCARD 12

Front: What is withdrawal/avoidance?
Back: Leaving conflict unresolved; used when stakes are low or emotions high.
Memory Hook: Avoid = not a solution.
Trigger Words: “not worth pursuing,” “cool-down period,” “low priority issue”

✅ FLASHCARD 13

Front: What is situational leadership?
Back: Leadership style that adapts to team maturity and circumstances.
Memory Hook: No one style fits all.
Trigger Words: “changing needs,” “adapting leadership,” “team maturity”

✅ FLASHCARD 14

Front: What should PM do first when a conflict emerges?
Back: Identify root cause by listening to all parties privately.
Memory Hook: Cause first → solution later.
Trigger Words: “root cause,” “hear all sides,” “understanding conflict”

✅ FLASHCARD 15

Front: What is active listening?
Back: Listening attentively, reflecting back, asking clarifying questions.
Memory Hook: Listen > Speak.
Trigger Words: “miscommunication,” “avoid assumptions”

✅ FLASHCARD 16

Front: What is the PM’s first action when team morale drops?
Back: Identify concerns through one-on-one discussions and adjust leadership approach.
Memory Hook: Morale down → talk privately.
Trigger Words: “frustration,” “disengagement,” “reduced collaboration”

✅ FLASHCARD 17

Front: Why is transparency important in leadership?
Back: Builds trust and increases team engagement.
Memory Hook: Transparency = trust.
Trigger Words: “team distrust,” “information withheld”

✅ FLASHCARD 18

Front: How should a PM handle negative stakeholder pressure on team members?
Back: Protect team by channeling communication and managing expectations.
Memory Hook: Shield team from unnecessary stress.
Trigger Words: “stakeholder pressure,” “team overwhelmed”

✅ FLASHCARD 19

Front: How should a PM handle poor interpersonal dynamics?
Back: Facilitate team-building activities and conflict resolution workshops.
Memory Hook: Interpersonal issues → team-building.
Trigger Words: “unhealthy relationships,” “team tension”

✅ FLASHCARD 20

Front: What’s the PM’s responsibility when misinformation spreads?
Back: Correct it quickly, clarify facts, update communication plans.
Memory Hook: Bad info → correct immediately.
Trigger Words: “rumors,” “incorrect assumptions,” “confusion”

✅ FLASHCARD 21

Front: What is the best way to influence without authority?
Back: Build trust, use expertise, demonstrate credibility, communicate persuasively.
Memory Hook: Influence = credibility + relationships.
Trigger Words: “matrix organization,” “indirect reporting”

✅ FLASHCARD 22

Front: What is the PM’s role in encouraging collaboration?
Back: Facilitate communication, break silos, create shared purpose.
Memory Hook: Collaboration doesn’t happen by accident.
Trigger Words: “cross-functional,” “handoff issues,” “alignment needed”

✅ FLASHCARD 23

Front: How does the PM ensure accountability?
Back: Clearly define ownership, track commitments, follow up consistently.
Memory Hook: Clear expectations + follow-up = accountability.
Trigger Words: “slipping deadlines,” “unclear ownership”

✅ FLASHCARD 24

Front: What is the PM’s responsibility in decision-making?
Back: Facilitate decisions, ensure data is available, ensure consensus where possible.
Memory Hook: PM facilitates—not dictates—decisions.
Trigger Words: “decision paralysis,” “no agreement,” “analysis needed”

✅ FLASHCARD 25

Front: What to do when a senior team member dominates discussions?
Back: Use facilitation to ensure equal participation.
Memory Hook: Balance voices in the room.
Trigger Words: “one person controlling,” “others silent”

✅ FLASHCARD 26

Front: What is constructive feedback?
Back: Specific, actionable, timely, and focused on behavior not personality.
Memory Hook: Clear → behavior-based → respectful.
Trigger Words: “feedback session,” “performance issue”

✅ FLASHCARD 27

Front: What is the PM’s role in coaching?
Back: Guide team members to solution through questions, not directives.
Memory Hook: Coach = ask, don’t tell.
Trigger Words: “skills development,” “growth,” “mentoring needed”

✅ FLASHCARD 28

Front: How should PM respond to cultural differences?
Back: Adapt communication, encourage sensitivity, clarify expectations.
Memory Hook: Culture shapes behavior.
Trigger Words: “global team,” “cultural misunderstanding”

✅ FLASHCARD 29

Front: What is conflict escalation?
Back: Formal process to involve higher authority when team cannot resolve issues.
Memory Hook: Escalate only after trying resolution.
Trigger Words: “standoff,” “unresolvable conflict,” “impasse”

✅ FLASHCARD 30

Front: When is escalation appropriate?
Back: When risks, delays, or team relations cannot be resolved internally.
Memory Hook: Used sparingly → last resort.
Trigger Words: “ongoing conflict,” “harm to project,” “team breakdown”

### 📘 SECTION 3: SUPPORT TEAM PERFORMANCE

✅ FLASHCARD 1

Front: What is the PM’s role in supporting team performance?
Back: Monitor team progress, remove impediments, provide feedback, motivate, and reinforce accountability.
Memory Hook: Support = monitor + clear barriers.
Trigger Words: “team not progressing,” “delays,” “blockers”

✅ FLASHCARD 2

Front: What is the purpose of performance appraisals?
Back: Evaluate individual/team contributions, identify strengths, and develop improvement plans.
Memory Hook: Appraisal = improvement, not punishment.
Trigger Words: “performance review,” “assessment needed”

✅ FLASHCARD 3

Front: What is a team performance assessment?
Back: Evaluates team effectiveness, collaboration, communication, and productivity.
Memory Hook: Team health check = TPA.
Trigger Words: “team dynamics,” “collaboration issues,” “ineffective teamwork”

✅ FLASHCARD 4

Front: What should PM do if team productivity decreases?
Back: Investigate root cause, hold one-on-one discussions, adjust workload, remove blockers.
Memory Hook: Decline → investigate → support.
Trigger Words: “reduced output,” “slower progress”

✅ FLASHCARD 5

Front: What tool is used to track individual and team commitments?
Back: Task board, Kanban board, burndown chart, or resource assignment matrix.
Memory Hook: Boards visualize accountability.
Trigger Words: “unclear tasks,” “work not visible”

✅ FLASHCARD 6

Front: What is the purpose of daily standups?
Back: Provide transparency, identify impediments, align team efforts.
Memory Hook: Standup = sync + unblock.
Trigger Words: “daily sync,” “agile team,” “impediments”

✅ FLASHCARD 7

Front: How should PM address repeated bottlenecks?
Back: Analyze root cause, escalate removal if needed, revisit workflow.
Memory Hook: Bottleneck = process fix.
Trigger Words: “work slowing,” “team blocked repeatedly”

✅ FLASHCARD 8

Front: What is the PM’s role in facilitating team collaboration?
Back: Encourage open communication, mediate disagreements, create shared understanding.
Memory Hook: Collaboration is PM-built.
Trigger Words: “team silos,” “miscommunication”

✅ FLASHCARD 9

Front: When should the PM intervene in team communication?
Back: When communication breakdown affects performance or relationships.
Memory Hook: Intervene when damage happening.
Trigger Words: “poor communication,” “conflict escalating”

✅ FLASHCARD 10

Front: What is constructive feedback?
Back: Feedback that is specific, actionable, timely, and focused on behavior, not personality.
Memory Hook: Correct constructively, not critically.
Trigger Words: “feedback session,” “performance improvement”

✅ FLASHCARD 11

Front: How often should feedback be delivered?
Back: Continuously throughout the project—not just at reviews.
Memory Hook: Feedback early, often, and informal.
Trigger Words: “ongoing issues,” “recurring mistakes”

✅ FLASHCARD 12

Front: What should the PM do if a team member repeatedly makes errors?
Back: Coach privately, identify root cause, provide training or mentoring.
Memory Hook: Mistakes → coach before escalate.
Trigger Words: “repeated errors,” “skill gap”

✅ FLASHCARD 13

Front: What is team ground rules?
Back: Agreed policies and behaviors that guide how team members interact.
Memory Hook: Ground rules = behavior expectations.
Trigger Words: “team conflict,” “lack of respect,” “behavior issues”

✅ FLASHCARD 14

Front: What should PM do when a team member challenges authority?
Back: Seek to understand concern privately and clarify expectations.
Memory Hook: Private talk > public confrontation.
Trigger Words: “challenging PM,” “undermining decisions”

✅ FLASHCARD 15

Front: What should PM do when team members ignore ground rules?
Back: Reinforce agreed norms, discuss impact, gain recommitment.
Memory Hook: Ground rules → reinforce, don’t punish.
Trigger Words: “rules ignored,” “behavior slipping”

✅ FLASHCARD 16

Front: What is the purpose of a team performance dashboard?
Back: Provides visual metrics for progress, quality, risks, and workload.
Memory Hook: Dashboard = transparency.
Trigger Words: “tracking metrics,” “KPI visibility”

✅ FLASHCARD 17

Front: How to handle a chronically negative team member?
Back: Address privately, identify issues, encourage positive participation.
Memory Hook: Negativity → address early.
Trigger Words: “toxic behavior,” “disengagement”

✅ FLASHCARD 18

Front: What is a performance improvement plan (PIP)?
Back: Formal plan outlining performance issues, expectations, and timelines for improvement.
Memory Hook: PIP = for serious issues only.
Trigger Words: “persistent underperformance,” “formal process needed”

✅ FLASHCARD 19

Front: How should PM handle workload imbalance?
Back: Re-evaluate resource allocation, redistribute tasks, level resources.
Memory Hook: Unbalanced load → reassign tasks.
Trigger Words: “overloaded member,” “burnout risk”

✅ FLASHCARD 20

Front: What is the PM's role during retrospectives?
Back: Facilitate improvement, gather lessons learned, help team refine processes.
Memory Hook: Retro → improve process next sprint.
Trigger Words: “agile retrospective,” “process improvement”

✅ FLASHCARD 21

Front: How should PM respond to recurring delays?
Back: Analyze workflow, identify root cause, optimize process, escalate if needed.
Memory Hook: Recurring = process problem.
Trigger Words: “repetitive delays,” “bottlenecks”

✅ FLASHCARD 22

Front: What is the best way to recognize team achievements?
Back: Provide timely, specific, and public recognition aligned to team values.
Memory Hook: Recognition fuels motivation.
Trigger Words: “successes,” “milestones achieved”

✅ FLASHCARD 23

Front: What is the difference between mentoring and coaching?
Back: Mentoring = long-term development; Coaching = specific skill improvement.
Memory Hook: Mentor = guide; Coach = skill boost.
Trigger Words: “career growth,” “specific improvement need”

✅ FLASHCARD 24

Front: What is conflict prevention?
Back: Ensuring clarity, communication, shared understanding, and aligned expectations.
Memory Hook: Prevent > cure.
Trigger Words: “avoid future conflict,” “proactive actions”

✅ FLASHCARD 25

Front: What should PM do when team feedback contradicts stakeholder expectations?
Back: Facilitate alignment and update communication plan as needed.
Memory Hook: Align team ↔ stakeholders.
Trigger Words: “misaligned expectations,” “stakeholder conflict”

✅ FLASHCARD 26

Front: How does psychological safety support team performance?
Back: Encourages sharing ideas, raising concerns, and open communication.
Memory Hook: Safe teams = high-performing teams.
Trigger Words: “fear of speaking,” “team withholding information”

✅ FLASHCARD 27

Front: What is servant leadership's role in performance?
Back: Removes obstacles, supports growth, promotes autonomy.
Memory Hook: Serve the team → team performs.
Trigger Words: “team blocked,” “lack support”

✅ FLASHCARD 28

Front: What should PM do when a key resource becomes unavailable?
Back: Reassess schedule, rebalance workload, request replacement if needed.
Memory Hook: Lost resource → revise plan.
Trigger Words: “sudden departure,” “resource lost”

✅ FLASHCARD 29

Front: What is the PM’s role when quality drops?
Back: Investigate cause, reassess workload, provide training, update processes.
Memory Hook: Quality issues = process + skill review.
Trigger Words: “defects increasing,” “poor outputs”

✅ FLASHCARD 30

Front: What is the PM responsibility when communication gaps arise?
Back: Facilitate communication, clarify channels, revisit communication plan.
Memory Hook: If communication breaks → reset channels.
Trigger Words: “misunderstanding,” “information lost”

### 📘 SECTION 4: EMPOWER TEAM MEMBERS & STAKEHOLDERS

✅ FLASHCARD 1

Front: What does “empowerment” mean in project management?
Back: Giving team members authority, tools, trust, and decision-making power to do their work independently.
Memory Hook: Empower = authority + support.
Trigger Words: “bottlenecks,” “approval delays,” “team waiting for PM”

✅ FLASHCARD 2

Front: What is the best leadership strategy to empower teams?
Back: Servant leadership—remove blockers, support autonomy, provide resources.
Memory Hook: Help the team → don’t control the team.
Trigger Words: “need more autonomy,” “blocked by PM”

✅ FLASHCARD 3

Front: What is the PM’s first step when team members lack authority to make decisions?
Back: Clarify decision rights and escalate for additional authority if needed.
Memory Hook: Authority + clarity = empowerment.
Trigger Words: “unclear decisions,” “waiting for approvals”

✅ FLASHCARD 4

Front: What is participative decision-making?
Back: Involving the team in decisions to increase buy-in and ownership.
Memory Hook: Involve team → better outcomes.
Trigger Words: “team input needed,” “lack of buy-in”

✅ FLASHCARD 5

Front: What is the role of the PM in building trust?
Back: Be transparent, consistent, and supportive while giving team space to own work.
Memory Hook: Trust is built through behavior, not words.
Trigger Words: “low trust,” “skepticism,” “hesitation”

✅ FLASHCARD 6

Front: What must a PM do before delegating work?
Back: Ensure the team has skills, authority, resources, and context.
Memory Hook: Delegate only when capable + authorized.
Trigger Words: “delegation,” “task assignment”

✅ FLASHCARD 7

Front: What is the risk of micromanagement?
Back: Reduces autonomy, lowers morale, kills innovation, increases dependency.
Memory Hook: Micromanage = demotivate.
Trigger Words: “PM controlling tasks,” “team frustrated”

✅ FLASHCARD 8

Front: When should PM escalate authority issues?
Back: When lack of authority blocks progress or causes delays.
Memory Hook: No authority = escalate.
Trigger Words: “blocked by management,” “approval bottleneck”

✅ FLASHCARD 9

Front: What is the PM’s responsibility when team members suggest improvements?
Back: Evaluate suggestions, incorporate viable ideas, empower ownership.
Memory Hook: Ideas → empower + implement.
Trigger Words: “innovation,” “process improvement suggestion”

✅ FLASHCARD 10

Front: What are influence skills?
Back: Ability to persuade without authority using relationships, communication, and expertise.
Memory Hook: Influence > authority.
Trigger Words: “no formal authority,” “matrix environment”

✅ FLASHCARD 11

Front: What is autonomy in a team?
Back: Freedom for team members to make decisions and manage tasks without constant oversight.
Memory Hook: Autonomy drives ownership.
Trigger Words: “self-organizing,” “independent decisions”

✅ FLASHCARD 12

Front: How does empowerment affect productivity?
Back: Empowered teams are more engaged, faster, and more innovative.
Memory Hook: Empowerment = velocity boost.
Trigger Words: “low productivity,” “slow decision-making”

✅ FLASHCARD 13

Front: What is resource empowerment?
Back: Giving team the tools, access, permissions, and knowledge to perform work effectively.
Memory Hook: Right tools = empowered team.
Trigger Words: “access blocked,” “missing tools,” “permissions needed”

✅ FLASHCARD 14

Front: What is the PM’s role in stakeholder empowerment?
Back: Involve stakeholders early, clarify expectations, provide transparency and feedback.
Memory Hook: Engage stakeholders → empower decisions.
Trigger Words: “stakeholder confusion,” “lack of involvement”

✅ FLASHCARD 15

Front: How does the PM empower stakeholders during requirement gathering?
Back: Provide platforms for input, encourage collaboration, ensure voices are heard.
Memory Hook: Stakeholders own requirements.
Trigger Words: “stakeholder misalignment,” “unclear needs”

✅ FLASHCARD 16

Front: What should PM do when stakeholders disagree?
Back: Facilitate discussion to align goals and reach consensus.
Memory Hook: PMI → Facilitate first, escalate last.
Trigger Words: “stakeholder conflict,” “opposing opinions”

✅ FLASHCARD 17

Front: What is the escalation path for unresolved stakeholder issues?
Back: Escalate to sponsor or governance board.
Memory Hook: Escalate only after facilitation attempts.
Trigger Words: “persistent disagreement,” “stakeholder deadlock”

✅ FLASHCARD 18

Front: What is the most important driver of empowerment?
Back: Trust between PM and team/stakeholders.
Memory Hook: Trust = autonomy + accountability.
Trigger Words: “lack of trust,” “fear of mistakes”

✅ FLASHCARD 19

Front: How should the PM handle decision paralysis?
Back: Provide structured decision-making tools (priority matrix, weighted scoring).
Memory Hook: Decision tools remove paralysis.
Trigger Words: “stuck,” “no decision,” “analysis overload”

✅ FLASHCARD 20

Front: What is a decision-making framework?
Back: A structured method (RACI, DACI, MOCHA, consensus, majority vote).
Memory Hook: Framework = consistency + clarity.
Trigger Words: “unclear roles,” “confusion in decisions”

✅ FLASHCARD 21

Front: What is the PM’s role in removing obstacles?
Back: Identify impediments, escalate barriers, coordinate support, eliminate roadblocks.
Memory Hook: PM = chief obstacle remover.
Trigger Words: “team blocked,” “impediments,” “process barriers”

✅ FLASHCARD 22

Front: What is the purpose of empowerment limits?
Back: Defines boundaries where decisions must be escalated due to risk, cost, or compliance.
Memory Hook: Empower with boundaries.
Trigger Words: “decision limit,” “budget threshold,” “risk escalation”

✅ FLASHCARD 23

Front: Why is accountability important?
Back: Ensures ownership, clarity, and reliability in execution.
Memory Hook: Accountability = follow-through.
Trigger Words: “missed deadlines,” “poor ownership”

✅ FLASHCARD 24

Front: How does empowerment impact creativity?
Back: Increases innovation by giving team freedom to propose and test ideas.
Memory Hook: Freedom → creativity.
Trigger Words: “need innovation,” “new solution needed”

✅ FLASHCARD 25

Front: How can PM empower a new or inexperienced team?
Back: Provide mentorship, training, context, and gradually increase autonomy.
Memory Hook: Start guided → grow autonomy.
Trigger Words: “new team,” “lack experience,” “hesitant team members”

### 📘 SECTION 5: ENSURE TEAM MEMBERS ARE TRAINED

✅ FLASHCARD 1

Front: What is the first step when identifying training needs?
Back: Conduct a skills assessment to determine gaps between required vs. existing skills.
Memory Hook: Skill gap → assess before action.
Trigger Words: “missing skills,” “need capability,” “unprepared team”

✅ FLASHCARD 2

Front: What is a skills gap analysis?
Back: A comparison of current team skills vs. skills required to complete project work.
Memory Hook: Gap analysis = baseline of competence.
Trigger Words: “unqualified,” “new technology,” “training required”

✅ FLASHCARD 3

Front: What is the PM’s responsibility after identifying a skill gap?
Back: Develop and implement a training plan with clear timelines and outcomes.
Memory Hook: Identify → Train → Verify.
Trigger Words: “team struggling,” “lack expertise”

✅ FLASHCARD 4

Front: What is cross-training?
Back: Training team members to perform multiple roles to increase flexibility.
Memory Hook: Cross-training = resilience.
Trigger Words: “dependency risk,” “single point of failure”

✅ FLASHCARD 5

Front: Why is ongoing training important?
Back: Ensures capability growth, adapts to project changes, and supports continuous improvement.
Memory Hook: Continuous learning = continuous improvement.
Trigger Words: “new tools,” “process changes,” “technology updates”

✅ FLASHCARD 6

Front: What should the PM do if the team lacks expertise in new technology?
Back: Arrange external training or bring in subject matter experts (SMEs).
Memory Hook: SME support → faster competence.
Trigger Words: “new software,” “emerging tech,” “unfamiliar system”

✅ FLASHCARD 7

Front: What type of training works best for Agile teams?
Back: Workshops, hands-on learning, pair programming, collaboration exercises.
Memory Hook: Agile training = experiential.
Trigger Words: “Agile adoption,” “new framework,” “scrum ceremonies”

✅ FLASHCARD 8

Front: When should training be conducted?
Back: As early as possible and continuously throughout the project as needs arise.
Memory Hook: Train early → avoid rework later.
Trigger Words: “need preparation,” “before development starts”

✅ FLASHCARD 9

Front: What is the PM’s role when training is insufficient?
Back: Reassess the training approach, supplement with coaching or external support.
Memory Hook: If training fails → adapt training method.
Trigger Words: “performance not improving,” “still unclear”

✅ FLASHCARD 10

Front: What is mentoring?
Back: Long-term developmental support provided by experienced professionals.
Memory Hook: Mentoring = long-term growth.
Trigger Words: “career development,” “experience gap”

✅ FLASHCARD 11

Front: What is coaching?
Back: Short-term, targeted guidance that focuses on performance improvement.
Memory Hook: Coaching = specific skill boost.
Trigger Words: “task-specific issues,” “need improvement quickly”

✅ FLASHCARD 12

Front: How does training support risk reduction?
Back: Enhances competence and reduces errors, dependency, and rework.
Memory Hook: Skilled team = lower risk.
Trigger Words: “error-prone work,” “inexperience causing delays”

✅ FLASHCARD 13

Front: What is knowledge transfer?
Back: Systematic sharing of information from SMEs to team members.
Memory Hook: Knowledge shared = resilience increased.
Trigger Words: “handoff,” “SME leaving,” “risk of knowledge loss”

✅ FLASHCARD 14

Front: What must PM ensure before delegating tasks?
Back: That team members are trained, capable, and have access to required resources.
Memory Hook: Delegate only when trained.
Trigger Words: “task assignment,” “readiness check”

✅ FLASHCARD 15

Front: What training tools can PM use?
Back: Workshops, simulations, online modules, coaching sessions, job shadowing.
Memory Hook: Training = multi-format.
Trigger Words: “team unprepared,” “learning needed”

✅ FLASHCARD 16

Front: What should PM do when training resources are limited?
Back: Prioritize critical skills, apply phased training, leverage internal experts.
Memory Hook: Prioritize high-impact skills.
Trigger Words: “budget limitations,” “resource constraints”

✅ FLASHCARD 17

Front: What is a training plan?
Back: A documented approach outlining who needs training, what type, when, and how success is measured.
Memory Hook: Training needs → plan, execute, measure.
Trigger Words: “learning roadmap,” “competency plan”

✅ FLASHCARD 18

Front: What is competency development?
Back: Structured process to improve skills, knowledge, and behaviors over time.
Memory Hook: Competency = capability for future tasks.
Trigger Words: “team maturity,” “skill building”

✅ FLASHCARD 19

Front: How is training effectiveness evaluated?
Back: By measuring performance improvements and verifying skills application.
Memory Hook: Evaluate → adjust → reinforce.
Trigger Words: “training review,” “results not showing”

✅ FLASHCARD 20

Front: What should PM do if lack of training causes repeated errors?
Back: Stop work if necessary, retrain immediately, and adjust training strategy.
Memory Hook: Training gaps → fix before proceeding.
Trigger Words: “same mistake repeating,” “quality issues”

✅ FLASHCARD 21

Front: What is the PM’s responsibility for stakeholder training?
Back: Ensure stakeholders understand processes, tools, and requirements relevant to their roles.
Memory Hook: Stakeholders also need training.
Trigger Words: “stakeholder confusion,” “misaligned expectations”

✅ FLASHCARD 22

Front: When should PM seek external trainers?
Back: When specialized knowledge is needed that the team lacks internally.
Memory Hook: Specialized = external expert.
Trigger Words: “advanced skill,” “new methodology”

✅ FLASHCARD 23

Front: What is just-in-time training?
Back: Training that occurs immediately before the task requiring the skill.
Memory Hook: Train right before use.
Trigger Words: “upcoming task,” “timing training”

✅ FLASHCARD 24

Front: What is the PM’s role in encouraging self-learning?
Back: Provide resources, time, motivation, and access to learning platforms.
Memory Hook: Self-learning → continuous growth.
Trigger Words: “learning culture,” “curiosity”

✅ FLASHCARD 25

Front: How does training align with project success?
Back: Ensures team members are capable, reduces risk, improves quality and efficiency.
Memory Hook: Training = success enabler.
Trigger Words: “success factors,” “team readiness,” “capability building”

### 📘 SECTION 6: BUILD SHARED UNDERSTANDING

✅ FLASHCARD 1

Front: What is “shared understanding” in project management?
Back: A mutual clarity about goals, requirements, roles, dependencies, and expectations across the team and stakeholders.
Memory Hook: If misunderstandings exist → shared understanding is missing.
Trigger Words: “confusion,” “inconsistent interpretation,” “unclear goals”

✅ FLASHCARD 2

Front: Which technique is the fastest way to build shared understanding?
Back: Facilitated workshops or collaborative working sessions.
Memory Hook: Get everyone in one place → align quickly.
Trigger Words: “alignment,” “kickoff,” “stakeholder collaboration”

✅ FLASHCARD 3

Front: What is the PM’s first action when team members provide conflicting information?
Back: Facilitate clarification meeting to align on facts and expectations.
Memory Hook: Conflicting info → clarify together.
Trigger Words: “mixed messages,” “misalignment,” “contradictions”

✅ FLASHCARD 4

Front: What document ensures shared understanding of requirements?
Back: Requirements documentation and the Requirements Traceability Matrix (RTM).
Memory Hook: RTM = one source of truth.
Trigger Words: “missing requirements,” “unapproved scope,” “no tracking”

✅ FLASHCARD 5

Front: What is the purpose of a communication plan?
Back: To define how information is created, shared, escalated, and archived for all parties.
Memory Hook: Communication plan = shared information flow.
Trigger Words: “miscommunication,” “unclear messaging,” “information gaps”

✅ FLASHCARD 6

Front: What is the best way to ensure stakeholders understand requirements?
Back: Use demos, prototypes, mock-ups, and collaborative reviews.
Memory Hook: Show, don’t just tell.
Trigger Words: “unclear expectations,” “need visual confirmation”

✅ FLASHCARD 7

Front: What is progressive elaboration?
Back: Clarifying and refining details as more information becomes available.
Memory Hook: Details evolve → update understanding.
Trigger Words: “early uncertainty,” “gradual clarity”

✅ FLASHCARD 8

Front: What is the PM’s responsibility when the team misinterprets requirements?
Back: Re-engage with stakeholders, clarify expectations, update RTM and communication plans.
Memory Hook: Misinterpretation = immediate clarification.
Trigger Words: “requirements gap,” “incorrect assumptions”

✅ FLASHCARD 9

Front: What tool ensures all requirements are linked to deliverables and tests?
Back: Requirements Traceability Matrix (RTM).
Memory Hook: RTM prevents scope gaps.
Trigger Words: “tracking requirements,” “verification needed”

✅ FLASHCARD 10

Front: What is the benefit of visual management (Kanban, charts, boards)?
Back: Increases transparency, reduces confusion, aligns team on current work status.
Memory Hook: Visual = universal understanding.
Trigger Words: “status unclear,” “team not synced”

✅ FLASHCARD 11

Front: What is a knowledge repository?
Back: A centralized location for storing project documents, decisions, and lessons learned.
Memory Hook: One source for all information.
Trigger Words: “lost information,” “can’t find documents”

✅ FLASHCARD 12

Front: Why are facilitated workshops effective?
Back: They reduce ambiguity, align stakeholders, and provide direct collaboration.
Memory Hook: Workshop = alignment accelerator.
Trigger Words: “ambiguity,” “uncertainty,” “varied expectations”

✅ FLASHCARD 13

Front: How does PM ensure cross-functional alignment?
Back: Communicate dependencies, clarify responsibilities, synchronize handoffs.
Memory Hook: Cross-team → clarify dependencies.
Trigger Words: “handoff issues,” “silos,” “team disconnect”

✅ FLASHCARD 14

Front: What should the PM do when stakeholders disagree about priorities?
Back: Facilitate prioritization workshop using objective criteria.
Memory Hook: Prioritization → group decision.
Trigger Words: “priority conflict,” “competing interests”

✅ FLASHCARD 15

Front: What is the purpose of assumptions and constraints logs?
Back: Capture expected conditions and limitations that influence shared understanding.
Memory Hook: Assumptions drive decisions → must verify.
Trigger Words: “team assumptions,” “unverified beliefs”

✅ FLASHCARD 16

Front: What technique ensures alignment during project start?
Back: Project kickoff meeting.
Memory Hook: Kickoff = set the tone + align purpose.
Trigger Words: “project beginning,” “initial alignment”

✅ FLASHCARD 17

Front: What is active listening?
Back: Listening with intent, asking clarifying questions, confirming understanding.
Memory Hook: Listen → Clarify → Confirm.
Trigger Words: “misunderstanding,” “lost context”

✅ FLASHCARD 18

Front: What should PM do when stakeholders do not understand technical details?
Back: Translate complex information into simple terms or visuals; avoid jargon.
Memory Hook: Simplify → clarify.
Trigger Words: “technical confusion,” “non-technical audience”

✅ FLASHCARD 19

Front: What is a communication escalation path?
Back: A defined sequence of whom to inform and when for issues or decisions.
Memory Hook: Escalate based on clarity + urgency.
Trigger Words: “stakeholder unresponsive,” “decision needed”

✅ FLASHCARD 20

Front: What is the PM’s role during requirement changes?
Back: Clarify changes with all stakeholders, update documentation, communicate impact.
Memory Hook: Change = alignment check.
Trigger Words: “scope changes,” “unclear impact,” “new requirement”

✅ FLASHCARD 21

Front: What is the purpose of a glossary or definitions list?
Back: Ensure consistent understanding of terminology across all parties.
Memory Hook: Shared language = shared understanding.
Trigger Words: “confusing terms,” “different interpretations”

✅ FLASHCARD 22

Front: What is team norming?
Back: Creating agreement on behaviors, communication, decision processes.
Memory Hook: Norms = unspoken rules made explicit.
Trigger Words: “behavior misalignment,” “unclear expectations”

✅ FLASHCARD 23

Front: How does PM handle misunderstandings between technical and business teams?
Back: Facilitate joint sessions to clarify terminology, goals, and assumptions.
Memory Hook: Bridge the gap → facilitate translation.
Trigger Words: “tech vs business disconnect,” “conflicting views”

✅ FLASHCARD 24

Front: What is knowledge sharing?
Back: Collaborative exchange of skills, insights, and information.
Memory Hook: Share knowledge → avoid dependencies.
Trigger Words: “knowledge hoarding,” “SME dependency”

✅ FLASHCARD 25

Front: What is the PM’s responsibility when information is interpreted differently?
Back: Re-communicate expectations clearly and verify understanding with all parties.
Memory Hook: Clarify → verify → align.
Trigger Words: “misinterpretation,” “mixed feedback,” “stakeholder confusion”

### 📘 SECTION 7: MANAGE CONFLICT

✅ FLASHCARD 1

Front: What is the first action a PM must take when conflict arises?
Back: Identify the root cause of the conflict by listening to all parties.
Memory Hook: Cause first → solution later.
Trigger Words: “conflict emerges,” “disagreement,” “tension building”

✅ FLASHCARD 2

Front: What is the preferred conflict resolution style according to PMI?
Back: Collaboration (win-win).
Memory Hook: Collaboration is the top PMI answer.
Trigger Words: “find best solution,” “all voices included”

✅ FLASHCARD 3

Front: What does collaboration involve?
Back: Open discussion, exploring needs, identifying root causes, and working together.
Memory Hook: Collaborate = root cause + consensus.
Trigger Words: “long-term resolution,” “team harmony”

✅ FLASHCARD 4

Front: When is compromise appropriate?
Back: When a quick temporary solution is needed and both parties must give a little.
Memory Hook: Compromise = partial win.
Trigger Words: “need quick resolution,” “both give up something”

✅ FLASHCARD 5

Front: What is smoothing (accommodating)?
Back: Emphasizing agreement and downplaying differences to maintain harmony.
Memory Hook: Smoothing = temporary peace.
Trigger Words: “calm tension,” “avoid conflict escalation”

✅ FLASHCARD 6

Front: When is smoothing most useful?
Back: When the issue is minor or emotions need calming before deeper discussion.
Memory Hook: Smooth to de-escalate emotions.
Trigger Words: “emotional conflict,” “minor disagreement”

✅ FLASHCARD 7

Front: What is withdrawal/avoidance?
Back: Stepping away from conflict without resolving it; used temporarily.
Memory Hook: Avoid = delay, not resolve.
Trigger Words: “cool down,” “not worth time,” “low priority”

✅ FLASHCARD 8

Front: When is withdrawal appropriate?
Back: When emotions are high or issue is trivial and not worth addressing now.
Memory Hook: Avoid only when low stakes.
Trigger Words: “heated argument,” “emotionally charged”

✅ FLASHCARD 9

Front: What is forcing?
Back: Using authority to impose a solution; win-lose outcome.
Memory Hook: Force rarely recommended.
Trigger Words: “deadline-critical,” “emergency decision,” “safety issue”

✅ FLASHCARD 10

Front: When is forcing appropriate?
Back: Only in emergencies, safety-critical situations, or when quick action is mandatory.
Memory Hook: Only for emergencies.
Trigger Words: “urgent,” “critical risk,” “immediate action needed”

✅ FLASHCARD 11

Front: What is the primary source of conflict in projects?
Back: Scarce or limited resources.
Memory Hook: Resources cause most conflicts.
Trigger Words: “resource allocation,” “overload,” “competition”

✅ FLASHCARD 12

Front: What are other common conflict sources?
Back: Schedules, priorities, technical opinions, cost, roles, personalities.
Memory Hook: Schedule + priorities + resources = biggest triggers.
Trigger Words: “priority conflict,” “role confusion”

✅ FLASHCARD 13

Front: What should the PM do when conflict escalates beyond team control?
Back: Escalate to sponsor or governance as last resort.
Memory Hook: Escalate only after attempts to resolve.
Trigger Words: “impasse,” “no resolution,” “continued conflict”

✅ FLASHCARD 14

Front: What is the PM’s role during conflict resolution?
Back: Facilitate discussion, ensure psychological safety, encourage mutual respect.
Memory Hook: PM = facilitator, not judge.
Trigger Words: “resolve disagreement,” “communication breakdown”

✅ FLASHCARD 15

Front: What is the first step if team members blame each other?
Back: Separate emotion from facts and identify root cause objectively.
Memory Hook: Facts > emotion.
Trigger Words: “finger pointing,” “defensiveness”

✅ FLASHCARD 16

Front: How should PM react when conflict becomes personal or emotional?
Back: Pause discussion, cool emotions, then reconvene with structured facilitation.
Memory Hook: Emotion → pause → reset.
Trigger Words: “heated argument,” “personal attacks”

✅ FLASHCARD 17

Front: What technique helps prevent future conflict?
Back: Establish clear ground rules, roles, expectations, and communication norms.
Memory Hook: Clarity prevents conflict.
Trigger Words: “recurring conflict,” “role confusion”

✅ FLASHCARD 18

Front: What is the PM’s approach when two SMEs disagree strongly?
Back: Facilitate a technical deep dive discussion to evaluate options objectively.
Memory Hook: Facts + criteria → resolution.
Trigger Words: “technical debate,” “expert disagreement”

✅ FLASHCARD 19

Front: How should PM handle conflict among remote team members?
Back: Use video calls, re-establish communication norms, increase clarity and transparency.
Memory Hook: Remote conflict → communicate visually.
Trigger Words: “virtual team,” “time zone conflict”

❇️ FLASHCARD 20

Front: What is the best way to avoid conflict escalation?
Back: Address issues early, maintain transparency, and foster open communication.
Memory Hook: Early intervention prevents blowups.
Trigger Words: “small issues growing,” “concerns ignored”

❇️ FLASHCARD 21

Front: How does emotional intelligence support conflict management?
Back: Helps PM understand emotions, manage reactions, and guide conversation constructively.
Memory Hook: EI = better conflict outcomes.
Trigger Words: “emotional triggers,” “sensitivity needed”

❇️ FLASHCARD 22

Front: What should PM do if conflict threatens project goals?
Back: Escalate according to governance protocols after attempting collaboration.
Memory Hook: Threat to project → escalate appropriately.
Trigger Words: “missed deadlines,” “delays due to conflict”

❇️ FLASHCARD 23

Front: What is conflict de-escalation?
Back: Actions to reduce tension and stabilize conversations before deeper discussion.
Memory Hook: Stabilize → then resolve.
Trigger Words: “heated exchange,” “tension high”

❇️ FLASHCARD 24

Front: What facilitation methods help resolve conflict?
Back: Active listening, restating points, establishing shared goals, structured dialogue.
Memory Hook: Facilitate → clarify → resolve.
Trigger Words: “moderate discussion,” “miscommunication”

❇️ FLASHCARD 25

Front: What is the PM’s responsibility to ensure conflicts don’t disrupt morale?
Back: Create psychologically safe environment, address issues early, reinforce norms.
Memory Hook: Safety + norms = team cohesion.
Trigger Words: “team stress,” “fear of speaking,” “decreasing morale”

## 📘 DOMAIN II — PROCESS (50%)

### ⭐ TASK 8: Execute Project With Urgency to Deliver Business Value

✅ FLASHCARD 8.1

Front: What does “urgency” mean in PMP terms?
Back: Removing blockers and delivering value early, not rushing.
Memory Hook: Urgency ≠ haste. It means BLOCKER REMOVAL.
Trigger Words: “delays,” “bottlenecks,” “need early value”

✅ FLASHCARD 8.2

Front: What is the PM’s first action when work stalls?
Back: Identify and remove impediments.
Memory Hook: Stall → unblock immediately.
Trigger Words: “stuck,” “waiting,” “dependency issues”

✅ FLASHCARD 8.3

Front: What should PM do when stakeholders demand fast delivery?
Back: Prioritize MVP and incremental value delivery.
Memory Hook: Deliver value early, not everything early.
Trigger Words: “accelerate,” “urgent timeline”

### ⭐ TASK 9: Manage Communications

✅ FLASHCARD 9.1

Front: Types of communication?
Back: Push, Pull, Interactive
Memory Hook: Push alerts, Pull archives, Interactive discussion.
Trigger Words: “email,” “meetings,” “status updates”

✅ FLASHCARD 9.2

Front: What is the PM’s first action when there’s miscommunication?
Back: Review and update the communications management plan.
Memory Hook: Plan first → fix breakdown.
Trigger Words: “mixed messages,” “stakeholder confusion”

✅ FLASHCARD 9.3

Front: What improves communication clarity?
Back: Tailoring message format, frequency, detail level per stakeholder needs.
Memory Hook: Right message → right audience.
Trigger Words: “wrong format,” “too much detail,” “not enough detail”

### ⭐ TASK 10: Assess and Manage Risks

✅ FLASHCARD 10.1

Front: What is the FIRST step when a new risk emerges?
Back: Document in risk register, then assess probability & impact.
Memory Hook: Document → analyze BEFORE acting.
Trigger Words: “new uncertainty,” “unexpected issue”

✅ FLASHCARD 10.2

Front: Negative risk responses?
Back: Avoid, Mitigate, Transfer, Accept
Memory Hook: AMTA.
Trigger Words: “threat,” “reduce impact,” “insurance”

✅ FLASHCARD 10.3

Front: Positive risk responses?
Back: Exploit, Enhance, Share, Accept
Memory Hook: EESA.
Trigger Words: “opportunity,” “benefit,” “leverage”

✅ FLASHCARD 10.4

Front: What is a risk trigger?
Back: Early warning sign that risk event may occur.
Memory Hook: Trigger = alarm bell.
Trigger Words: “indicator,” “threshold approaching”

### ⭐ TASK 11: Engage Stakeholders

✅ FLASHCARD 11.1

Front: First action when a new stakeholder is identified?
Back: Add to stakeholder register and analyze influence/interest.
Memory Hook: Update register BEFORE action.
Trigger Words: “new participant,” “late joiner”

✅ FLASHCARD 11.2

Front: What is stakeholder engagement assessment?
Back: Compares current vs desired engagement levels.
Memory Hook: Gap analysis for people.
Trigger Words: “resistance,” “uninvolved,” “over-involved”

### ⭐ TASK 12: Plan and Manage Scope

✅ FLASHCARD 12.1

Front: What prevents scope creep?
Back: Formal change control and stable scope baseline.
Memory Hook: Unauthorized change = scope creep.
Trigger Words: “add this quickly,” “just a small change”

✅ FLASHCARD 12.2

Front: What is the WBS?
Back: A deliverable-based decomposition of project work.
Memory Hook: WBS = WHAT, not how.
Trigger Words: “break down work,” “scope clarity”

### ⭐ TASK 13: Plan and Manage Schedule

✅ FLASHCARD 13.1

Front: What is critical path?
Back: Longest path that determines project duration; zero float.
Memory Hook: No slack = critical.
Trigger Words: “delay impacts end date”

✅ FLASHCARD 13.2

Front: What is fast-tracking?
Back: Doing activities in parallel that were sequential.
Memory Hook: Parallel = more risk.
Trigger Words: “accelerate schedule,” “overlap tasks”

✅ FLASHCARD 13.3

Front: What is crashing?
Back: Adding resources to shorten duration at higher cost.
Memory Hook: Crash = cost ↑ time ↓.
Trigger Words: “need faster,” “cost flexibility”

### ⭐ TASK 14: Plan and Manage Budget and Resources

✅ FLASHCARD 14.1

Front: CPI < 1 means what?
Back: Cost overrun.
Memory Hook: CPI < 1 = cost problem.
Trigger Words: “over budget,” “inefficient”

✅ FLASHCARD 14.2

Front: SPI < 1 means what?
Back: Behind schedule.
Memory Hook: SPI < 1 = behind.
Trigger Words: “behind on timeline”

✅ FLASHCARD 14.3

Front: ETC formula (typical performance)?
Back: (BAC – EV) / CPI
Memory Hook: Remaining ÷ performance rate.
Trigger Words: “forecast,” “cost projection”

### ⭐ TASK 15: Plan and Manage Quality

✅ FLASHCARD 15.1

Front: QA vs QC?
Back: QA = process; QC = product.
Memory Hook: A = Audit, C = Check.
Trigger Words: “prevention,” “inspection”

✅ FLASHCARD 15.2

Front: Which tool to find root cause of defects?
Back: Fishbone (Ishikawa) diagram.
Memory Hook: Fishbone = cause analysis.
Trigger Words: “why defects,” “cause unknown”

### ⭐ TASK 16: Integrate Project Planning Activities

✅ FLASHCARD 16.1

Front: What is the integrated project plan?
Back: A consolidated master plan combining all subsidiary plans.
Memory Hook: Integration = unify everything.
Trigger Words: “planning alignment,” “cross-team impact”

✅ FLASHCARD 16.2

Front: What method updates plans progressively?
Back: Rolling wave planning.
Memory Hook: Plan detailed later for unknown areas.
Trigger Words: “uncertainty,” “high-level now”

### ⭐ TASK 17: Manage Project Changes

✅ FLASHCARD 17.1

Front: Correct change control sequence?
Back: Document → Analyze → CCB → Approve/Reject → Update plans → Communicate.
Memory Hook: Never skip analysis.
Trigger Words: “change request,” “stakeholder asks to modify”

✅ FLASHCARD 17.2

Front: What is the CCB?
Back: Change Control Board that reviews/approves changes.
Memory Hook: CCB = gatekeeper.
Trigger Words: “formal approval,” “impact review”

### ⭐ TASK 18: Manage Procurement

✅ FLASHCARD 18.1

Front: Who carries risk in fixed-price contracts?
Back: The seller.
Memory Hook: FP = seller risk.
Trigger Words: “cost certainty,” “fixed deliverable”

✅ FLASHCARD 18.2

Front: What is a procurement statement of work (SOW)?
Back: A document that defines what the seller must deliver.
Memory Hook: SOW = seller instructions.
Trigger Words: “vendor work definition”

### ⭐ TASK 19: Manage Project Artifacts

✅ FLASHCARD 19.1

Front: What is a lessons learned register?
Back: A living document capturing insights during execution.
Memory Hook: Update continually—not just at end.
Trigger Words: “what worked,” “what didn’t”

✅ FLASHCARD 19.2

Front: What is configuration management?
Back: Processes for identifying and controlling changes to documents/products.
Memory Hook: Keep versions under control.
Trigger Words: “document control,” “versioning”

### ⭐ TASK 20: Determine Appropriate Project Methodology

✅ FLASHCARD 20.1

Front: When use Agile?
Back: High uncertainty, fast change, customer collaboration.
Memory Hook: Change-friendly → Agile.
Trigger Words: “evolving scope,” “frequent updates”

✅ FLASHCARD 20.2

Front: When use Predictive?
Back: Stable requirements, fixed scope, regulatory environments.
Memory Hook: Stable → Predictive.
Trigger Words: “fixed scope,” “clear upfront requirements”

### ⭐ TASK 21: Establish Project Governance Structure

✅ FLASHCARD 21.1

Front: What is governance?
Back: Framework defining authority, decision rights, and oversight.
Memory Hook: Governance = rules & authority.
Trigger Words: “who decides,” “approval flow”

### ⭐ TASK 22: Manage Project Issues

✅ FLASHCARD 22.1

Front: What is an issue?
Back: A problem that has already occurred and needs action.
Memory Hook: Issue = current, risk = future.
Trigger Words: “happening now,” “needs resolution”

### ⭐ TASK 23: Ensure Knowledge Transfer

✅ FLASHCARD 23.1

Front: Why is knowledge transfer critical?
Back: Reduces dependency risks and prepares team for sustainment.
Memory Hook: Knowledge shared = no bottleneck.
Trigger Words: “handoff,” “SME leaving”

### ⭐ TASK 24: Plan and Manage Project Closure

✅ FLASHCARD 24.1

Front: What is required for closure?
Back: Administrative closeout, contract closure, final reports, lessons learned.
Memory Hook: Close contracts FIRST.
Trigger Words: “finalization,” “handoff”

### 📘 DOMAIN II — SECTION 1 (TASK 8) COMPLETE FLASHCARD SET

✅ FLASHCARD 1

Front: What does “execute with urgency” mean in PMP terms?
Back: Removing blockers quickly and enabling early value delivery—not rushing or cutting quality.
Memory Hook: Urgency = unblock + deliver value, NOT rush.
Trigger Words: “bottlenecks,” “work stalled,” “need to move faster”

✅ FLASHCARD 2

Front: What is the PM’s FIRST action when progress slows?
Back: Identify impediments and remove the blockers affecting flow.
Memory Hook: Stalled work → remove obstacles first.
Trigger Words: “stuck,” “delayed,” “waiting on inputs”

✅ FLASHCARD 3

Front: What should the PM prioritize when urgency is required?
Back: Delivering MVP or high-value incremental releases.
Memory Hook: Value early > Full scope early.
Trigger Words: “accelerate,” “need speed,” “early benefits”

✅ FLASHCARD 4

Front: What is the PM’s role in managing workflow?
Back: Optimize flow, reduce waiting, escalate blockers, limit WIP (work in progress).
Memory Hook: Flow > speed.
Trigger Words: “slow throughput,” “queue buildup”

✅ FLASHCARD 5

Front: How should PM respond when repeated impediments occur?
Back: Conduct root cause analysis and implement systemic fixes.
Memory Hook: Recurring blockers = process problem.
Trigger Words: “constant delays,” “same issue repeating”

✅ FLASHCARD 6

Front: What tool visualizes workflow and bottlenecks?
Back: Kanban board or similar visual management system.
Memory Hook: Visual = bottlenecks visible.
Trigger Words: “lack visibility,” “too many tasks in progress”

✅ FLASHCARD 7

Front: What is the PM’s role when dependencies are blocking progress?
Back: Coordinate cross-team dependencies, escalate if necessary, negotiate resources.
Memory Hook: Dependencies = coordination + escalation.
Trigger Words: “handoff issues,” “external team delays”

✅ FLASHCARD 8

Front: How does the PM ensure continuous value delivery?
Back: Deliver increments frequently, validate with stakeholders, adjust based on feedback.
Memory Hook: Deliver → Validate → Adjust.
Trigger Words: “value stream,” “continuous delivery”

✅ FLASHCARD 9

Front: What should PM do when a team member reports a blocker?
Back: Address immediately, escalate if the PM cannot resolve directly.
Memory Hook: Blocker = immediate action.
Trigger Words: “impediment,” “waiting,” “stuck”

✅ FLASHCARD 10

Front: What is the PM’s responsibility in urgent situations?
Back: Remove red tape, expedite decisions, support team autonomy.
Memory Hook: Urgency = empower team.
Trigger Words: “waiting for approval,” “decision bottleneck”

✅ FLASHCARD 11

Front: How can PM encourage team ownership?
Back: Empower team members with authority and involve them in decision-making.
Memory Hook: Ownership = empowerment + autonomy.
Trigger Words: “waiting for PM,” “unclear authority”

✅ FLASHCARD 12

Front: What enables faster execution?
Back: Clear priorities, focused work, minimal multitasking.
Memory Hook: Multitasking slows urgency.
Trigger Words: “too many tasks,” “context-switching”

✅ FLASHCARD 13

Front: What should PM do when stakeholders demand acceleration without clarity?
Back: Clarify prioritization, negotiate trade-offs, adjust scope to achieve MVP.
Memory Hook: Speed requires clarity + tradeoffs.
Trigger Words: “go faster,” “increase delivery pressure”

✅ FLASHCARD 14

Front: What is the relationship between urgency and quality?
Back: Urgency requires removing delays, not lowering standards.
Memory Hook: Urgency ≠ cutting corners.
Trigger Words: “rush,” “pressure to skip steps”

✅ FLASHCARD 15

Front: How does the PM protect the team during urgent execution?
Back: Shield from unnecessary interruptions, control scope, and resolve escalations.
Memory Hook: Protect team > absorb pressure.
Trigger Words: “stakeholder pressure,” “scope push”

✅ FLASHCARD 16

Front: What is the PM’s responsibility regarding risk during urgency?
Back: Continuously reassess risks and avoid shortcuts that increase risk exposure.
Memory Hook: Urgency increases risk → monitor closely.
Trigger Words: “fast-tracking,” “compressed timeline”

✅ FLASHCARD 17

Front: What tool helps identify workflow inefficiencies?
Back: Value Stream Mapping.
Memory Hook: Map → find waste → remove delays.
Trigger Words: “waste,” “process inefficiency”

✅ FLASHCARD 18

Front: What should the PM do when different teams have conflicting urgencies?
Back: Align dependencies, clarify priorities with stakeholders, negotiate sequence.
Memory Hook: Alignment fixes conflicting priorities.
Trigger Words: “cross-team conflict,” “priority mismatch”

✅ FLASHCARD 19

Front: What is the PM’s role in ensuring urgency is sustainable?
Back: Balance demand with team capacity, prevent burnout, manage pace.
Memory Hook: Sustainable urgency > burnout.
Trigger Words: “overwork,” “long hours,” “team stress”

✅ FLASHCARD 20

Front: When should PM escalate urgency-related issues?
Back: When delays exceed PM authority or require higher-level resource decisions.
Memory Hook: Escalate when authority ends.
Trigger Words: “blocked by external team,” “need executive decision”

### 📘 DOMAIN II – SECTION 2 (TASK 9) COMPLETE FLASHCARD SET

✅ FLASHCARD 1

Front: What is the main purpose of the Communications Management Plan?
Back: Defines how, when, by whom, and in what format project information will be communicated.
Memory Hook: Plan = blueprint for communication.
Trigger Words: “who needs what info,” “frequency,” “format”

✅ FLASHCARD 2

Front: What are the three communication types?
Back: Push, Pull, Interactive
Memory Hook: Push = send; Pull = access; Interactive = discussion.
Trigger Words: “email,” “portal,” “meeting”

✅ FLASHCARD 3

Front: What is the PM’s FIRST action when miscommunication occurs?
Back: Review the communications management plan and adjust it.
Memory Hook: Fix the plan before fixing the people.
Trigger Words: “confusion,” “misaligned expectations”

✅ FLASHCARD 4

Front: What is the purpose of stakeholder communication tailoring?
Back: Adjusts content, frequency, and format to stakeholder needs and preferences.
Memory Hook: Right info → right person → right way.
Trigger Words: “too much detail,” “not enough detail”

✅ FLASHCARD 5

Front: What should PM do when stakeholders ignore communications?
Back: Confirm preferred communication channels, adjust format, and follow up personally.
Memory Hook: Ignored message → wrong method.
Trigger Words: “not reading emails,” “unresponsive stakeholder”

✅ FLASHCARD 6

Front: What is a communication escalation path?
Back: Defines who to escalate to, when, and in what sequence.
Memory Hook: Escalate based on urgency + impact.
Trigger Words: “stakeholder unresponsive,” “urgent decision required”

✅ FLASHCARD 7

Front: What is the PM’s role in maintaining communication flow?
Back: Ensure information is accurate, timely, accessible, and understood.
Memory Hook: PM = communication integrator.
Trigger Words: “multiple teams,” “misinformation”

✅ FLASHCARD 8

Front: What tool helps visualize communication needs?
Back: Stakeholder Engagement Assessment Matrix or communication matrix.
Memory Hook: Matrix clarifies who gets what.
Trigger Words: “unclear communication responsibilities”

✅ FLASHCARD 9

Front: What is active listening in project communication?
Back: Listening intently, clarifying, restating, and confirming understanding.
Memory Hook: Listen > Speak.
Trigger Words: “misunderstanding,” “lack of clarity”

✅ FLASHCARD 10

Front: What should PM do when different stakeholders receive conflicting information?
Back: Verify facts, correct misinformation, re-align communication channels.
Memory Hook: Correct fast → prevent escalation.
Trigger Words: “contradictory updates,” “confusion spreading”

### ⭐ ADVANCED COMMUNICATION FLASHCARDS (PMI EXAM-LEVEL)

✅ FLASHCARD 11

Front: What is communication noise?
Back: Interference that distorts message clarity (language, culture, technology, assumptions).
Memory Hook: Remove noise → improve clarity.
Trigger Words: “language barrier,” “misinterpretation”

✅ FLASHCARD 12

Front: What is the formula for communication channels?
Back: n(n – 1) / 2
Memory Hook: More people = exponentially more channels.
Trigger Words: “team size,” “complexity”

✅ FLASHCARD 13

Front: What should PM do when a stakeholder misinterprets a written message?
Back: Switch to interactive communication (meeting/call) to clarify.
Memory Hook: When unclear → speak live.
Trigger Words: “email misread,” “tone unclear”

✅ FLASHCARD 14

Front: How should PM handle confidential communications?
Back: Secure channels, limited access, and need-to-know distribution.
Memory Hook: Confidential = protected + restricted.
Trigger Words: “sensitive info,” “legal risk”

✅ FLASHCARD 15

Front: What is the PM’s role when stakeholders request excessive updates?
Back: Balance requests against schedule overhead; negotiate frequency based on value.
Memory Hook: Communicate effectively, not excessively.
Trigger Words: “too many meetings,” “status fatigue”

### ⭐ COMMUNICATION EXECUTION & MONITORING

✅ FLASHCARD 16

Front: What is work performance information used for in communication?
Back: Provides analyzed insights for status reports.
Memory Hook: Data → information → report.
Trigger Words: “variance,” “forecast,” “dashboard”

✅ FLASHCARD 17

Front: What should PM do when communication is creating conflict?
Back: Facilitate alignment meeting, clarify roles, reset expectations.
Memory Hook: Conflict from communication = clarify + re-align.
Trigger Words: “stakeholder disagreement,” “unclear ownership”

✅ FLASHCARD 18

Front: What are project communications?
Back: Status reports, dashboards, meeting minutes, decisions, escalations.
Memory Hook: Communications = project heartbeat.
Trigger Words: “reports,” “updates,” “documentation”

### ⭐ HIGH-STAKES COMMUNICATION FLASHCARDS

✅ FLASHCARD 19

Front: What should PM do during executive communication?
Back: Provide concise, high-level summaries focusing on decisions and impacts.
Memory Hook: Executives want decisions, not details.
Trigger Words: “executive update,” “leadership summary”

✅ FLASHCARD 20

Front: What is the PM’s response when sponsor provides unclear direction?
Back: Ask clarifying questions and confirm expectations in writing.
Memory Hook: Clarity protects the project.
Trigger Words: “ambiguous instruction,” “mixed message from sponsor”

### 📘 DOMAIN II — SECTION 3 (TASK 10) COMPLETE FLASHCARD SET

#### 🔹 RISK FOUNDATIONS

✅ FLASHCARD 1

Front: What is the FIRST action when a new risk is identified?
Back: Record it in the risk register → then assess probability & impact.
Memory Hook: Document → Analyze BEFORE acting.
Trigger Words: “new risk,” “unexpected event,” “discovery”

✅ FLASHCARD 2

Front: What is the Risk Register?
Back: A document containing all identified risks, owners, triggers, responses, and status.
Memory Hook: Risk Register = living risk database.
Trigger Words: “risk list,” “risk owner,” “risk tracking”

✅ FLASHCARD 3

Front: What is the difference between risk and issue?
Back: Risk = future uncertainty. Issue = current problem.
Memory Hook: Risk = future, Issue = now.
Trigger Words: “already happened,” “potential event”

#### 🔹 RISK ANALYSIS (QUALITATIVE)

✅ FLASHCARD 4

Front: What is qualitative risk analysis?
Back: Prioritizes risks based on probability & impact using expert judgment.
Memory Hook: Qualitative = fast prioritization.
Trigger Words: “probability,” “impact,” “P-I matrix”

✅ FLASHCARD 5

Front: What is a probability and impact matrix?
Back: A grid to score risks and prioritize based on severity.
Memory Hook: Hot spots = focus first.
Trigger Words: “high probability,” “high impact”

✅ FLASHCARD 6

Front: What is a risk trigger?
Back: Early warning sign that a risk is likely to occur.
Memory Hook: Trigger = alarm bell.
Trigger Words: “indicator,” “early warning”

✅ FLASHCARD 7

Front: What is risk categorization?
Back: Grouping risks by type (technical, schedule, cost, operational).
Memory Hook: Group to see patterns.
Trigger Words: “risk breakdown structure,” “patterns”

#### 🔹 RISK ANALYSIS (QUANTITATIVE)

✅ FLASHCARD 8

Front: What is quantitative risk analysis?
Back: Numerical analysis of effects on schedule and cost using data models.
Memory Hook: Quantitative = numbers + simulation.
Trigger Words: “expected monetary value,” “Monte Carlo”

✅ FLASHCARD 9

Front: What is Monte Carlo simulation?
Back: A simulation that shows probability of completing on time or within budget.
Memory Hook: Monte Carlo = probability forecast.
Trigger Words: “simulation,” “random variables”

✅ FLASHCARD 10

Front: What is Expected Monetary Value (EMV)?
Back: EMV = Probability × Impact (positive or negative).
Memory Hook: Probability × Impact = value.
Trigger Words: “decision tree,” “financial risk”

#### 🔹 RISK RESPONSE STRATEGIES (NEGATIVE THREATS)

✅ FLASHCARD 11

Front: What are the negative risk responses?
Back: Avoid, Mitigate, Transfer, Accept
Memory Hook: AMTA.
Trigger Words: “threat,” “reduce,” “transfer to third party”

✅ FLASHCARD 12

Front: When to use Avoid?
Back: When risk is too dangerous—change plan to eliminate it.
Memory Hook: Avoid = eliminate risk entirely.
Trigger Words: “unsafe,” “must not occur”

✅ FLASHCARD 13

Front: When to use Mitigate?
Back: Reduce probability or impact through preventive action.
Memory Hook: Mitigate = reduce, not eliminate.
Trigger Words: “reduce chance,” “reduce severity”

✅ FLASHCARD 14

Front: When to use Transfer?
Back: Shift risk to third party (insurance, warranty, FP contract).
Memory Hook: Transfer = someone else's problem (for a fee).
Trigger Words: “outsourcing,” “insurance,” “contracting”

✅ FLASHCARD 15

Front: When to use Accept?
Back: When cost of response outweighs benefit or risk is low/moderate.
Memory Hook: Accept = tolerate with monitoring.
Trigger Words: “low impact,” “no action,” “risk tolerance”

#### 🔹 RISK RESPONSE STRATEGIES (POSITIVE OPPORTUNITIES)

✅ FLASHCARD 16

Front: What are positive risk responses?
Back: Exploit, Enhance, Share, Accept
Memory Hook: EESA.
Trigger Words: “opportunities,” “benefit maximization”

✅ FLASHCARD 17

Front: When to use Exploit?
Back: Ensure the opportunity definitely occurs.
Memory Hook: Exploit = guarantee benefit.
Trigger Words: “high-value opportunity,” “must happen”

✅ FLASHCARD 18

Front: When to use Enhance?
Back: Increase probability or impact of opportunity.
Memory Hook: Enhance = make more likely.
Trigger Words: “increase benefits,” “boost chance”

✅ FLASHCARD 19

Front: When to use Share?
Back: Partner with another party to realize opportunity.
Memory Hook: Share = share gain + share work.
Trigger Words: “joint venture,” “partners”

✅ FLASHCARD 20

Front: When to use Accept (positive)?
Back: Take no proactive action; be ready if opportunity happens.
Memory Hook: Positive accept = passive uplift.
Trigger Words: “low likelihood,” “small opportunity”

#### 🔹 RISK MONITORING & CONTROL

✅ FLASHCARD 21

Front: What is a risk audit?
Back: Examines effectiveness of risk responses and process improvements.
Memory Hook: Audit = effectiveness check.
Trigger Words: “quality of risk management,” “review”

✅ FLASHCARD 22

Front: What is risk re-assessment?
Back: Periodic review of risk register to identify new risks and retire old ones.
Memory Hook: Reassess frequently.
Trigger Words: “ongoing review,” “update register”

✅ FLASHCARD 23

Front: What should PM do when risk response fails?
Back: Implement contingency plan → if that fails, use fallback plan.
Memory Hook: Plan A then Plan B.
Trigger Words: “contingency activated,” “didn’t work”

✅ FLASHCARD 24

Front: What is residual risk?
Back: Risk that remains after implementing a response.
Memory Hook: Residual = leftover.
Trigger Words: “remaining risk,” “after mitigation”

✅ FLASHCARD 25

Front: What is secondary risk?
Back: Risk that arises as a result of implementing a risk response.
Memory Hook: Fix creates new risk.
Trigger Words: “new risk created by response”

#### 🔹 RISK OWNERSHIP & GOVERNANCE

✅ FLASHCARD 26

Front: What is a risk owner?
Back: The person responsible for monitoring a risk and executing its response.
Memory Hook: Each risk → one owner.
Trigger Words: “assigned responsibility,” “monitoring”

✅ FLASHCARD 27

Front: What should PM do when a risk has no assigned owner?
Back: Assign ownership immediately and update the risk register.
Memory Hook: Ownerless risks = unmanaged risks.
Trigger Words: “no accountability,” “unassigned”

✅ FLASHCARD 28

Front: What is the PM’s role in risk communication?
Back: Ensure stakeholders understand risk status, responses, and impacts.
Memory Hook: Communicate → align → mitigate.
Trigger Words: “risk reporting,” “stakeholder update”

❇️ FLASHCARD 29

Front: What risks get escalated to governance bodies?
Back: High-impact, cross-team, or executive-level risks outside PM control.
Memory Hook: Escalate when authority ends.
Trigger Words: “enterprise risk,” “beyond control”

❇️ FLASHCARD 30

Front: Why is risk management ongoing?
Back: Risks evolve as project conditions change.
Memory Hook: Risk = dynamic, not one-time.
Trigger Words: “change request,” “scope change,” “new information”

### 📘 DOMAIN II – SECTION 4 (TASK 11) COMPLETE FLASHCARD SET

#### 🔹 STAKEHOLDER IDENTIFICATION

✅ FLASHCARD 1

Front: What is the FIRST action when a new stakeholder is identified?
Back: Add them to the stakeholder register and analyze their influence and interest.
Memory Hook: Register → Analyze → Engage.
Trigger Words: “new stakeholder,” “late discovery”

✅ FLASHCARD 2

Front: What information is recorded in the stakeholder register?
Back: Name, role, power/interest, expectations, impact, engagement level.
Memory Hook: Who + Power + Needs.
Trigger Words: “stakeholder details,” “classification”

#### 🔹 STAKEHOLDER ANALYSIS

✅ FLASHCARD 3

Front: What is stakeholder analysis used for?
Back: To understand stakeholder needs, expectations, influence, and engagement approach.
Memory Hook: Know them to engage them.
Trigger Words: “interest,” “power,” “influence”

✅ FLASHCARD 4

Front: What is the Stakeholder Engagement Assessment Matrix?
Back: Compares current vs desired engagement levels for each stakeholder.
Memory Hook: C → D gap = engagement plan.
Trigger Words: “resistant,” “neutral,” “supportive”

✅ FLASHCARD 5

Front: What should PM do when stakeholder engagement level is too low?
Back: Update engagement strategies and customize communication.
Memory Hook: Low engagement → adjust strategy.
Trigger Words: “stakeholder not involved,” “no interest”

#### 🔹 STAKEHOLDER COMMUNICATION

✅ FLASHCARD 6

Front: What is the PM’s primary responsibility in stakeholder communication?
Back: Ensure accurate, timely, tailored, and two-way communication.
Memory Hook: Communicate → Verify → Adapt.
Trigger Words: “expectation mismatch,” “miscommunication”

✅ FLASHCARD 7

Front: How does PM handle conflicting stakeholder requirements?
Back: Facilitate resolution, align priorities, escalate if necessary.
Memory Hook: Facilitate first, escalate last.
Trigger Words: “priority conflict,” “competing needs”

✅ FLASHCARD 8

Front: What should PM do when stakeholder expectations are unrealistic?
Back: Present data, constraints, risks, and negotiate feasible outcomes.
Memory Hook: Data = reality alignment.
Trigger Words: “unrealistic demands,” “scope pressure”

#### 🔹 STAKEHOLDER ENGAGEMENT STRATEGIES

✅ FLASHCARD 9

Front: How can PM increase stakeholder engagement?
Back: Provide early involvement, access to information, participative decision-making.
Memory Hook: Involve → Inform → Empower.
Trigger Words: “stakeholder not engaged,” “feedback missing”

✅ FLASHCARD 10

Front: What is the most effective method to engage stakeholders?
Back: Interactive communication (meetings, workshops, discussions).
Memory Hook: Talking beats emailing.
Trigger Words: “alignment needed,” “solve conflict”

✅ FLASHCARD 11

Front: What tool supports engagement optimization?
Back: Stakeholder engagement plan.
Memory Hook: Plan how to manage people.
Trigger Words: “improve engagement,” “communication plan update”

#### 🔹 TRACKING & MONITORING ENGAGEMENT

✅ FLASHCARD 12

Front: How does PM measure stakeholder engagement effectiveness?
Back: Compare actual engagement vs planned engagement levels, adjust strategy.
Memory Hook: Compare → Assess → Adjust.
Trigger Words: “engagement metrics,” “stakeholder survey”

✅ FLASHCARD 13

Front: What should PM do when stakeholder disengages suddenly?
Back: Investigate cause, re-engage through direct communication, clarify expectations.
Memory Hook: Disengagement → reconnect.
Trigger Words: “no response,” “lost interest”

✅ FLASHCARD 14

Front: What is the best way to sustain engagement long term?
Back: Maintain transparency, involve stakeholders in decisions, frequent feedback loops.
Memory Hook: Transparency builds trust.
Trigger Words: “long project,” “stakeholder fatigue”

#### 🔹 MANAGING RESISTANT OR DIFFICULT STAKEHOLDERS

✅ FLASHCARD 15

Front: What should PM do with resistant stakeholders?
Back: Understand concerns, address fears, communicate benefits, build trust.
Memory Hook: Resistance hides fear.
Trigger Words: “pushback,” “negative feedback”

✅ FLASHCARD 16

Front: When stakeholder actively opposes the project, what is PM’s approach?
Back: Engage privately, use empathy, uncover motivations, escalate if harmful.
Memory Hook: Private talk → root cause.
Trigger Words: “sabotage,” “opposition”

✅ FLASHCARD 17

Front: How should PM manage stakeholders with high power and low interest?
Back: Keep satisfied—inform major decisions without overwhelming them.
Memory Hook: High power = keep satisfied.
Trigger Words: “executives,” “board-level”

✅ FLASHCARD 18

Front: How should PM manage stakeholders with high interest but low power?
Back: Keep informed—engage frequently and seek feedback.
Memory Hook: High interest = keep informed.
Trigger Words: “end users,” “team-level stakeholders”

#### 🔹 ESCALATION & GOVERNANCE

✅ FLASHCARD 19

Front: When should PM escalate stakeholder issues?
Back: When conflicts cannot be resolved directly or impact project success.
Memory Hook: Escalate only when required.
Trigger Words: “impasse,” “critical conflict”

❇️ FLASHCARD 20

Front: Who typically resolves high-level stakeholder conflicts?
Back: Sponsor or governance board.
Memory Hook: Sponsor = escalation point.
Trigger Words: “executive conflict,” “authority needed”

### 📘 DOMAIN II — SECTION 5 (TASK 12) COMPLETE FLASHCARD SET

#### 🔹 SCOPE PLANNING FUNDAMENTALS

✅ FLASHCARD 1

Front: What is the first step in scope planning?
Back: Collect requirements from stakeholders.
Memory Hook: Understand needs before defining scope.
Trigger Words: “requirements,” “stakeholder input,” “needs gathering”

✅ FLASHCARD 2

Front: What is the Scope Management Plan?
Back: Document describing how scope will be defined, validated, and controlled.
Memory Hook: Plan how to manage what’s included.
Trigger Words: “scope control,” “scope definition”

✅ FLASHCARD 3

Front: What documents form the scope baseline?
Back: Project Scope Statement + WBS + WBS Dictionary.
Memory Hook: Scope baseline = S + WBS + WD.
Trigger Words: “baseline,” “approved scope”

#### 🔹 REQUIREMENTS MANAGEMENT

✅ FLASHCARD 4

Front: What is the Requirements Traceability Matrix (RTM)?
Back: Tool that links requirements to deliverables, tests, and acceptance criteria.
Memory Hook: RTM = ensure nothing is missed.
Trigger Words: “traceability,” “requirement mapping”

✅ FLASHCARD 5

Front: What is the PM’s first action when requirements conflict?
Back: Facilitate stakeholder discussion to reach alignment.
Memory Hook: Facilitate first, escalate last.
Trigger Words: “conflicting requirements,” “unclear priorities”

✅ FLASHCARD 6

Front: What should PM do when requirements are unclear?
Back: Clarify with stakeholders using workshops, prototypes, or interviews.
Memory Hook: Clarify → validate → document.
Trigger Words: “ambiguity,” “uncertainty”

#### 🔹 WBS & SCOPE STRUCTURE

✅ FLASHCARD 7

Front: What is the WBS?
Back: Hierarchical decomposition of project deliverables.
Memory Hook: WBS = deliverables, not tasks.
Trigger Words: “breakdown,” “decomposition”

✅ FLASHCARD 8

Front: What is NOT included in the WBS?
Back: Activities or tasks.
Memory Hook: WBS = WHAT, schedule shows HOW.
Trigger Words: “task list,” “not activities”

✅ FLASHCARD 9

Front: What is the WBS Dictionary?
Back: Detailed descriptions of each WBS component: scope, owner, acceptance criteria.
Memory Hook: Dictionary = definition.
Trigger Words: “work package details,” “clarify deliverables”

#### 🔹 PREVENTING & MANAGING SCOPE CREEP

✅ FLASHCARD 10

Front: What is scope creep?
Back: Uncontrolled change to scope without formal approval.
Memory Hook: Unauthorized change = creep.
Trigger Words: “just add this,” “quick fix”

✅ FLASHCARD 11

Front: How can PM prevent scope creep?
Back: Use formal change control and maintain a stable baseline.
Memory Hook: Controlled change only.
Trigger Words: “out of scope,” “unapproved changes”

✅ FLASHCARD 12

Front: What is gold plating?
Back: Adding extra features beyond requirements.
Memory Hook: Extra = waste + risk.
Trigger Words: “over-delivery,” “unasked enhancements”

✅ FLASHCARD 13

Front: What should PM do when team members add features without approval?
Back: Stop immediately, review baseline, enforce change control.
Memory Hook: Gold plating = stop + reset.
Trigger Words: “added feature,” “team exceeded scope”

#### 🔹 SCOPE VERIFICATION & VALIDATION

✅ FLASHCARD 14

Front: What is Validate Scope?
Back: Formal acceptance of completed deliverables by customer/stakeholders.
Memory Hook: Validation = customer acceptance.
Trigger Words: “accept deliverable,” “sign-off”

✅ FLASHCARD 15

Front: What is Verify Scope vs Control Quality?
Back: Verify Scope = customer acceptance; Control Quality = internal checking.
Memory Hook: Quality = internal; Validation = external.
Trigger Words: “inspection,” “approval”

✅ FLASHCARD 16

Front: What is the PM’s action when deliverables are rejected?
Back: Document defects, plan rework, update quality and requirements documents.
Memory Hook: Rejection = revise + rework.
Trigger Words: “not accepted,” “defects found”

#### 🔹 CHANGE CONTROL & SCOPE MANAGEMENT

✅ FLASHCARD 17

Front: What is the correct sequence for scope change control?
Back: Request → Analyze → CCB Review → Approve/Reject → Update Baselines.
Memory Hook: Never skip analysis.
Trigger Words: “change request,” “scope adjustment”

✅ FLASHCARD 18

Front: Who approves changes to scope baseline?
Back: Change Control Board (CCB) or authorized sponsor.
Memory Hook: CCB = scope guardian.
Trigger Words: “approval authority”

✅ FLASHCARD 19

Front: What should PM do when stakeholders attempt to bypass change control?
Back: Enforce the change process and explain impact on time/cost/quality.
Memory Hook: Protect the baseline.
Trigger Words: “urgent request,” “skip process”

#### 🔹 MONITORING SCOPE

✅ FLASHCARD 20

Front: What indicates scope is not well-managed?
Back: Frequent rework, change requests, discrepancies in deliverable expectations.
Memory Hook: Symptoms → scope misalignment.
Trigger Words: “rework,” “missing requirements”

✅ FLASHCARD 21

Front: What tool helps monitor scope performance?
Back: Variance analysis comparing scope baseline vs actual deliverable progress.
Memory Hook: Variance highlights drift.
Trigger Words: “scope deviation,” “performance metrics”

✅ FLASHCARD 22

Front: What performance metrics relate to scope?
Back: Requirements completion %, deliverable acceptance %, rework rate.
Memory Hook: Scope = deliverable performance.
Trigger Words: “progress report,” “KPI”

#### 🔹 AGILE/HYBRID SCOPE MANAGEMENT

✅ FLASHCARD 23

Front: How is scope managed in Agile?
Back: Through backlog refinement, iteration planning, and customer feedback.
Memory Hook: Flexible scope + fixed time.
Trigger Words: “backlog,” “priority changes,” “iterations”

✅ FLASHCARD 24

Front: What does Agile use instead of a WBS?
Back: Product backlog with epics, features, and user stories.
Memory Hook: Backlog = dynamic WBS.
Trigger Words: “user story,” “feature”

❇️ FLASHCARD 25

Front: What is the PM’s role in hybrid scope environment?
Back: Balance fixed predictive elements with flexible Agile work.
Memory Hook: Hybrid = stable + adaptive.
Trigger Words: “mixed approach,” “iteration + planning”

### 📘 DOMAIN II – SECTION 6 (TASK 13) COMPLETE FLASHCARD SET

#### 🔹 SCHEDULE PLANNING BASICS

✅ FLASHCARD 1

Front: What is the first step in schedule planning?
Back: Define and sequence activities based on WBS deliverables.
Memory Hook: Sequence follows scope.
Trigger Words: “activity definition,” “logical order”

✅ FLASHCARD 2

Front: What is the Schedule Management Plan?
Back: Defines how the schedule will be developed, monitored, updated, and controlled.
Memory Hook: Plan how to build and manage time.
Trigger Words: “schedule control,” “update process”

#### 🔹 ACTIVITY SEQUENCING & NETWORK DIAGRAMS

✅ FLASHCARD 3

Front: What tool shows dependencies and sequence of activities?
Back: Network diagram (Precedence Diagramming Method).
Memory Hook: Arrows = order.
Trigger Words: “PDM,” “dependencies,” “flow”

✅ FLASHCARD 4

Front: Types of dependencies?
Back: FS (Finish-Start), SS, FF, SF.
Memory Hook: FS is most common.
Trigger Words: “relationship type,” “logic link”

✅ FLASHCARD 5

Front: What are dependency categories?
Back: Mandatory, Discretionary, External, Internal.
Memory Hook: MD-EI.
Trigger Words: “constraints,” “outside influence”

#### 🔹 CRITICAL PATH & FLOAT

✅ FLASHCARD 6

Front: What is the Critical Path?
Back: Longest path through network; determines earliest project finish; zero float.
Memory Hook: No slack = critical.
Trigger Words: “delay = delay entire project”

✅ FLASHCARD 7

Front: What is total float?
Back: Amount of time an activity can be delayed without impacting project finish.
Memory Hook: Float = flexibility.
Trigger Words: “slack,” “wiggle room”

✅ FLASHCARD 8

Front: What is free float?
Back: Time an activity can be delayed without delaying successor activity.
Memory Hook: Free float = doesn’t affect next task.
Trigger Words: “successor,” “buffer”

#### 🔹 ESTIMATING METHODS

✅ FLASHCARD 9

Front: What is analogous estimating?
Back: Uses historical data; fast but less accurate.
Memory Hook: Analogy = approximate.
Trigger Words: “similar project,” “top-down estimate”

✅ FLASHCARD 10

Front: What is parametric estimating?
Back: Uses statistical or unit-based formulas for precision.
Memory Hook: Units × rate.
Trigger Words: “per unit,” “data-driven”

✅ FLASHCARD 11

Front: What is bottom-up estimating?
Back: Estimate at lowest level of WBS; most accurate.
Memory Hook: Small pieces → total.
Trigger Words: “work package,” “detailed estimate”

✅ FLASHCARD 12

Front: What is three-point estimating?
Back: Uses optimistic, pessimistic, most likely estimates.
Memory Hook: O + M + P.
Trigger Words: “uncertainty,” “PERT”

✅ FLASHCARD 13

Front: PERT formula?
Back: (O + 4M + P) / 6
Memory Hook: Weighted most likely.
Trigger Words: “PERT calculation”

#### 🔹 SCHEDULE COMPRESSION TECHNIQUES

✅ FLASHCARD 14

Front: What is fast-tracking?
Back: Overlapping activities that were sequential—higher risk.
Memory Hook: Parallel = risk ↑.
Trigger Words: “accelerate,” “compress timeline”

✅ FLASHCARD 15

Front: What is crashing?
Back: Adding resources to shorten duration; increases cost.
Memory Hook: Cost ↑ time ↓.
Trigger Words: “extra staff,” “budget impact”

✅ FLASHCARD 16

Front: When should fast-tracking be used?
Back: When there is no extra budget but higher risk is acceptable.
Memory Hook: Cheap but risky.
Trigger Words: “overlap,” “sequencing change”

✅ FLASHCARD 17

Front: When should crashing be used?
Back: When cost increases are acceptable but schedule reduction is essential.
Memory Hook: Spend money to save time.
Trigger Words: “urgent deadline,” “can add resources”

#### 🔹 BASELINE & SCHEDULE CONTROL

✅ FLASHCARD 18

Front: What is the schedule baseline?
Back: Approved version of the schedule, used to measure performance.
Memory Hook: Baseline = benchmark.
Trigger Words: “approved plan,” “variance tracking”

✅ FLASHCARD 19

Front: What causes schedule variance?
Back: Delays, inaccurate estimates, resource shortages, scope changes.
Memory Hook: Variance = deviation from plan.
Trigger Words: “behind schedule,” “SPI < 1”

✅ FLASHCARD 20

Front: What is schedule variance formula?
Back: SV = EV – PV
Memory Hook: Earned vs planned.
Trigger Words: “performance check,” “variance analysis”

✅ FLASHCARD 21

Front: What is Schedule Performance Index (SPI)?
Back: SPI = EV / PV
Memory Hook: SPI < 1 = behind, SPI > 1 = ahead.
Trigger Words: “efficiency,” “progress”

#### 🔹 MONITORING & CONTROLLING SCHEDULE

✅ FLASHCARD 22

Front: What does it mean if SPI < 1?
Back: Project is behind schedule.
Memory Hook: Less than 1 = losing time.
Trigger Words: “delay,” “underperforming”

✅ FLASHCARD 23

Front: What should PM do when schedule variance is detected?
Back: Investigate root causes and develop recovery plan.
Memory Hook: Investigate → respond.
Trigger Words: “slippage,” “tracking issues”

✅ FLASHCARD 24

Front: What is the PM’s role when schedule performance declines?
Back: Adjust resources, re-sequence activities, escalate bottlenecks.
Memory Hook: Fix bottlenecks.
Trigger Words: “resource shortage,” “critical path impacted”

❇️ FLASHCARD 25

Front: What indicates a potential future schedule risk?
Back: Frequent rework, dependency delays, poor estimates.
Memory Hook: Symptoms predict delay.
Trigger Words: “trending behind,” “dependency risk”

#### 🔹 AGILE/HYBRID SCHEDULING

❇️ FLASHCARD 26

Front: How is scheduling done in Agile?
Back: Fixed-length iterations with flexible scope.
Memory Hook: Time fixed → scope flexible.
Trigger Words: “sprint,” “iteration”

❇️ FLASHCARD 27

Front: What is a burndown chart used for?
Back: Shows remaining work vs time within a sprint.
Memory Hook: Burn down = work decreasing.
Trigger Words: “sprint tracking,” “trend”

❇️ FLASHCARD 28

Front: What is a release plan?
Back: Higher-level roadmap connecting multiple iterations to business goals.
Memory Hook: Big picture of sprints.
Trigger Words: “roadmap,” “delivery planning”

❇️ FLASHCARD 29

Front: What should PM do when Agile team velocity fluctuates heavily?
Back: Investigate causes, remove impediments, stabilize processes.
Memory Hook: Velocity = health indicator.
Trigger Words: “unpredictable output,” “inconsistent sprints”

❇️ FLASHCARD 30

Front: How do hybrid schedules function?
Back: Predictive components for fixed elements + Agile for evolving components.
Memory Hook: Hybrid = stable + adaptive.
Trigger Words: “mixed approach,” “integration”

### 📘 DOMAIN II — SECTION 7 (TASK 14) COMPLETE FLASHCARD SET

#### 🔹 COST & BUDGET FOUNDATIONS

✅ FLASHCARD 1

Front: What is the first step in cost planning?
Back: Estimate costs for each work package or activity.
Memory Hook: Estimate before budget.
Trigger Words: “cost planning,” “estimation”

✅ FLASHCARD 2

Front: What forms the cost baseline?
Back: Summed costs of all activities + contingency reserves.
Memory Hook: Baseline = estimate + contingency.
Trigger Words: “approved budget,” “baseline cost”

✅ FLASHCARD 3

Front: What is NOT included in cost baseline?
Back: Management reserves (they are outside the PM's control).
Memory Hook: Management reserve ≠ baseline.
Trigger Words: “unknown unknowns,” “executive-controlled”

#### 🔹 EARNED VALUE MANAGEMENT (EVM)

✅ FLASHCARD 4

Front: What is Planned Value (PV)?
Back: Budgeted cost for work scheduled to be completed by a specific date.
Memory Hook: Planned = expected by now.
Trigger Words: “schedule baseline,” “planned cost”

✅ FLASHCARD 5

Front: What is Earned Value (EV)?
Back: Budgeted cost of work actually completed by a specific date.
Memory Hook: Earned = progress achieved.
Trigger Words: “completed work,” “performance”

✅ FLASHCARD 6

Front: What is Actual Cost (AC)?
Back: Actual money spent for work completed.
Memory Hook: AC = what we paid.
Trigger Words: “expenditure,” “actual cost”

✅ FLASHCARD 7

Front: What is Cost Variance (CV)?
Back: CV = EV – AC
Memory Hook: Negative CV = over budget.
Trigger Words: “budget performance,” “overspending”

❇️ FLASHCARD 8

Front: What is CV < 0?
Back: Project is over budget.
Memory Hook: Negative bad.
Trigger Words: “cost overrun,” “red flag”

❇️ FLASHCARD 9

Front: What is Schedule Variance (SV)?
Back: SV = EV – PV
Memory Hook: Behind vs ahead.
Trigger Words: “time performance,” “progress”

❇️ FLASHCARD 10

Front: What is SPI?
Back: SPI = EV / PV
Memory Hook: SPI < 1 = behind schedule.
Trigger Words: “efficiency,” “schedule index”

❇️ FLASHCARD 11

Front: What is CPI?
Back: CPI = EV / AC
Memory Hook: CPI < 1 = cost overrun.
Trigger Words: “cost efficiency,” “spending control”

#### 🔹 FORECASTING & COST CONTROL

✅ FLASHCARD 12

Front: What is Estimate at Completion (EAC)?
Back: Forecasted total project cost based on current performance.
Memory Hook: Final expected cost.
Trigger Words: “forecast,” “projected total”

❇️ FLASHCARD 13

Front: EAC formula (typical performance)?
Back: EAC = BAC / CPI
Memory Hook: Budget / cost performance.
Trigger Words: “standard forecasting”

❇️ FLASHCARD 14

Front: EAC formula (atypical conditions)?
Back: EAC = AC + (BAC – EV)
Memory Hook: Actual + remaining.
Trigger Words: “anomaly,” “unexpected changes”

❇️ FLASHCARD 15

Front: What is ETC (Estimate to Complete)?
Back: ETC = EAC – AC
Memory Hook: Remaining cost.
Trigger Words: “cost to finish”

❇️ FLASHCARD 16

Front: What should PM do when CPI < 1?
Back: Investigate root cause, adjust spending, re-estimate remaining work.
Memory Hook: Cost inefficiency = corrective action.
Trigger Words: “over budget,” “cost variance”

❇️ FLASHCARD 17

Front: What does VAC (Variance at Completion) measure?
Back: VAC = BAC – EAC
Memory Hook: If VAC negative → over budget.
Trigger Words: “final cost difference”

#### 🔹 RESOURCE MANAGEMENT

❇️ FLASHCARD 18

Front: What is the Resource Management Plan?
Back: Defines how team and physical resources are acquired, managed, and released.
Memory Hook: Plan people + equipment.
Trigger Words: “staffing,” “resource handling”

❇️ FLASHCARD 19

Front: What is resource leveling?
Back: Adjusts schedule based on resource availability, may extend timeline.
Memory Hook: Level = delay to stabilize.
Trigger Words: “over-allocation,” “workload balance”

❇️ FLASHCARD 20

Front: What is resource smoothing?
Back: Adjusts resource use within limits of the existing schedule constraints.
Memory Hook: Smooth = balance without delay.
Trigger Words: “peak resource usage,” “optimize without delay”

❇️ FLASHCARD 21

Front: What should PM do when a key resource becomes unavailable?
Back: Re-allocate work, revise schedule, escalate for replacement.
Memory Hook: Lost resource → adjust plan.
Trigger Words: “critical resource lost,” “availability shift”

#### 🔹 COST CONTROL & CHANGE MANAGEMENT

❇️ FLASHCARD 22

Front: What is PM’s role in cost control?
Back: Monitor spending, forecast variance, and implement corrective actions.
Memory Hook: Track → forecast → correct.
Trigger Words: “cost monitoring,” “trend analysis”

❇️ FLASHCARD 23

Front: What triggers a cost baseline change?
Back: Approved change request (scope/schedule impact triggers cost change).
Memory Hook: Cost baseline only changes with approval.
Trigger Words: “baseline shift,” “change request”

❇️ FLASHCARD 24

Front: What should PM do when cost increases are requested?
Back: Perform impact analysis and submit change request to CCB.
Memory Hook: Analyze → approve → update.
Trigger Words: “budget increase,” “funding request”

#### 🔹 AGILE/HYBRID COST MANAGEMENT

❇️ FLASHCARD 25

Front: How does Agile manage cost differently?
Back: Fixed cost (team) + fixed time; scope varies each iteration.
Memory Hook: Cost fixed → scope adjusts.
Trigger Words: “stable budget,” “timeboxed iteration”

❇️ FLASHCARD 26

Front: What is velocity used for in Agile cost forecasting?
Back: Predict work output → estimate cost per iteration.
Memory Hook: Velocity = capacity = cost predictability.
Trigger Words: “future sprints,” “burn rate”

❇️ FLASHCARD 27

Front: What should PM do when Agile team burn rate increases unexpectedly?
Back: Investigate causes, optimize processes, adjust team allocation if needed.
Memory Hook: Burn rate = spending health.
Trigger Words: “cost spike,” “inefficiency”

### 📘 DOMAIN II — SECTION 8 (TASK 15) COMPLETE FLASHCARD SET

#### 🔹 QUALITY FOUNDATIONS

✅ FLASHCARD 1

Front: What is the difference between quality and grade?
Back: Quality = how well requirements are met; Grade = category or ranking of product features.
Memory Hook: High grade ≠ high quality.
Trigger Words: “premium vs basic,” “meets requirements”

✅ FLASHCARD 2

Front: What is the first step in quality planning?
Back: Identify quality requirements and standards.
Memory Hook: Define quality before measuring it.
Trigger Words: “quality criteria,” “standards,” “acceptance criteria”

#### 🔹 QUALITY MANAGEMENT PLAN

✅ FLASHCARD 3

Front: What does the Quality Management Plan define?
Back: How quality will be planned, implemented, monitored, and controlled.
Memory Hook: Plan how to assure and control quality.
Trigger Words: “quality plan,” “quality approach”

✅ FLASHCARD 4

Front: What are the key outputs of quality planning?
Back: Quality metrics, checklists, and quality management plan.
Memory Hook: Metrics + Checklists = measurable quality.
Trigger Words: “standards,” “requirements,” “quality measures”

#### 🔹 QA VS QC (IMPORTANT FOR EXAM)

✅ FLASHCARD 5

Front: What is Quality Assurance (QA)?
Back: Process-focused; ensures proper processes are followed.
Memory Hook: Assurance = process.
Trigger Words: “audit,” “process check”

✅ FLASHCARD 6

Front: What is Quality Control (QC)?
Back: Product-focused; identifies defects in deliverables.
Memory Hook: Control = detect defects.
Trigger Words: “inspection,” “testing,” “validation”

✅ FLASHCARD 7

Front: Validate Scope vs Control Quality?
Back: Validate Scope = customer acceptance; Control Quality = internal inspection.
Memory Hook: Customer vs internal.
Trigger Words: “signoff,” “customer review”

#### 🔹 QUALITY TOOLS (PMI FAVORITES)

✅ FLASHCARD 8

Front: What is a cause-and-effect diagram?
Back: Ishikawa (fishbone) diagram used for root-cause analysis.
Memory Hook: Fishbone = causes.
Trigger Words: “root cause,” “defects”

✅ FLASHCARD 9

Front: What is a Pareto chart used for?
Back: Identifies the most significant issues (80/20 rule).
Memory Hook: Focus on vital few.
Trigger Words: “prioritization,” “defects distribution”

✅ FLASHCARD 10

Front: What is a control chart used for?
Back: Monitors process stability and variation over time.
Memory Hook: Control limits = process health.
Trigger Words: “UCL,” “LCL,” “out of control”

❇️ FLASHCARD 11

Front: What indicates a process is out of control on a control chart?
Back: Data point outside control limits OR non-random patterns.
Memory Hook: Outside limits = fix process.
Trigger Words: “unstable process,” “special cause variation”

❇️ FLASHCARD 12

Front: What is a check sheet?
Back: Simple data collection tool to track defects or events.
Memory Hook: Checklist = data capture.
Trigger Words: “counting defects,” “pattern analysis”

❇️ FLASHCARD 13

Front: What is a flowchart used for?
Back: Visualizes process steps to identify improvements or bottlenecks.
Memory Hook: Flowchart = find inefficiencies.
Trigger Words: “process mapping,” “workflow analysis”

#### 🔹 COST OF QUALITY (COQ)

❇️ FLASHCARD 14

Front: What are the components of cost of quality?
Back: Prevention, Appraisal, Internal failure, External failure (PAIE).
Memory Hook: Invest early, save later.
Trigger Words: “quality cost,” “defect cost”

❇️ FLASHCARD 15

Front: Prevention costs include what?
Back: Training, planning, documentation, process improvement.
Memory Hook: Prevent defects before they occur.
Trigger Words: “training,” “process design”

❇️ FLASHCARD 16

Front: Appraisal costs include what?
Back: Inspections, testing, audits.
Memory Hook: Appraise = check quality.
Trigger Words: “testing,” “review,” “audit”

❇️ FLASHCARD 17

Front: What are internal failure costs?
Back: Rework, scrap, defects found before reaching customer.
Memory Hook: Internal = in-house waste.
Trigger Words: “rework,” “fix,” “scrap”

❇️ FLASHCARD 18

Front: What are external failure costs?
Back: Warranty claims, returns, recalls, customer dissatisfaction.
Memory Hook: External = expensive!
Trigger Words: “customer defect,” “return,” “lawsuits”

#### 🔹 QUALITY IMPROVEMENT & CONTINUOUS IMPROVEMENT

❇️ FLASHCARD 19

Front: What is continuous improvement called in Agile?
Back: Kaizen (improvement through retrospectives).
Memory Hook: Change small → improve big.
Trigger Words: “retrospective,” “process improvement”

❇️ FLASHCARD 20

Front: What is PDCA cycle?
Back: Plan → Do → Check → Act.
Memory Hook: Loop to improve.
Trigger Words: “continuous improvement,” “quality cycle”

❇️ FLASHCARD 21

Front: What should PM do when defects trend upward?
Back: Investigate root cause, adjust processes, implement corrective actions.
Memory Hook: Trending defects = fix process.
Trigger Words: “defects increasing,” “quality decline”

#### 🔹 QUALITY IN AGILE AND HYBRID PROJECTS

❇️ FLASHCARD 22

Front: How is quality ensured in Agile?
Back: Frequent testing, continuous integration, customer feedback, Definition of Done.
Memory Hook: Quality built every iteration.
Trigger Words: “DoD,” “acceptance criteria”

❇️ FLASHCARD 23

Front: What is the Definition of Done (DoD)?
Back: Clear checklist that work must meet to be considered complete.
Memory Hook: Done = no ambiguity.
Trigger Words: “acceptance,” “completion criteria”

❇️ FLASHCARD 24

Front: What is the PM’s role in hybrid quality management?
Back: Balance Agile flexibility with predictive quality standards.
Memory Hook: Hybrid = mix structure + adaptability.
Trigger Words: “mixed methods,” “compliance + feedback”

#### 🔹 QUALITY TROUBLESHOOTING (PMI EXAM LOGIC)

❇️ FLASHCARD 25

Front: What should PM do when customer rejects deliverables?
Back: Review acceptance criteria, correct defects, and reinforce QC processes.
Memory Hook: Rejection = revisit criteria + fix.
Trigger Words: “not accepted,” “failed review”

❇️ FLASHCARD 26

Front: What should PM do when team wants to reduce testing to save time?
Back: Reject the proposal—testing is part of quality control and cannot be skipped.
Memory Hook: Testing is non-negotiable.
Trigger Words: “cut corners,” “shorten process”

❇️ FLASHCARD 27

Front: What should PM do when defects persist despite fixes?
Back: Conduct root cause analysis and adjust processes (not just rework).
Memory Hook: Fix the process, not just the product.
Trigger Words: “repeated defects,” “recurring issues”

### 📘 DOMAIN II — SECTION 9 (TASK 16) COMPLETE FLASHCARD SET

#### 🔹 INTEGRATION MANAGEMENT PRINCIPLES

✅ FLASHCARD 1

Front: What is the purpose of integration planning?
Back: To unify all subsidiary plans into a cohesive, aligned project management plan.
Memory Hook: Integration = one master plan.
Trigger Words: “consolidate,” “align plans”

✅ FLASHCARD 2

Front: What documents make up the project management plan?
Back: All subsidiary plans (scope, schedule, cost, quality, resources, risk, procurement, communications, stakeholders).
Memory Hook: Master plan = all subplans.
Trigger Words: “comprehensive plan,” “integrated plan”

#### 🔹 PLANNING ALIGNMENT & CONSISTENCY

✅ FLASHCARD 3

Front: What is the PM’s first action when a subsidiary plan changes?
Back: Assess cross-plan impacts before updating the integrated plan.
Memory Hook: Analyze impacts before updating.
Trigger Words: “change request,” “plan modification”

✅ FLASHCARD 4

Front: What ensures consistency between different planning areas?
Back: Integrated change control and continuous alignment checks.
Memory Hook: Consistency = coordination.
Trigger Words: “alignment,” “cross-impact”

✅ FLASHCARD 5

Front: What should PM do if scope changes impact schedule and cost plans?
Back: Update all affected subsidiary plans and re-baseline if necessary.
Memory Hook: Change in one area → update all impacted areas.
Trigger Words: “ripple effect,” “multi-area impact”

#### 🔹 WORK PLANNING & COORDINATION

✅ FLASHCARD 6

Front: What is the PM’s role in coordinating planning activities?
Back: Facilitate cross-functional collaboration to build realistic and aligned plans.
Memory Hook: PM = integrator, not author of every plan.
Trigger Words: “cross-team,” “collaboration needed”

✅ FLASHCARD 7

Front: What is rolling wave planning?
Back: Progressive detailing of plans as information becomes available.
Memory Hook: Plan now for what’s known; detail later.
Trigger Words: “uncertainty,” “progressive elaboration”

✅ FLASHCARD 8

Front: What should PM do when teams create plans in isolation?
Back: Bring teams together for alignment and integration sessions.
Memory Hook: Silos break integration.
Trigger Words: “inconsistent assumptions,” “misalignment”

#### 🔹 DOCUMENTING ASSUMPTIONS & CONSTRAINTS

✅ FLASHCARD 9

Front: What are assumptions in project planning?
Back: Factors believed to be true without proof, affecting planning decisions.
Memory Hook: Assumption = unverified belief.
Trigger Words: “uncertainty,” “estimated condition”

✅ FLASHCARD 10

Front: What are constraints?
Back: Limitations (time, cost, scope, quality, resources) that restrict planning.
Memory Hook: Constraints = limits.
Trigger Words: “fixed date,” “fixed budget”

✅ FLASHCARD 11

Front: Why capture assumptions?
Back: They influence decisions and must be validated or monitored.
Memory Hook: Assumptions drive risk.
Trigger Words: “verify,” “dependency risk”

#### 🔹 DEPENDENCIES & INTERFACES

✅ FLASHCARD 12

Front: What should PM do when planning reveals critical cross-team dependencies?
Back: Document them, assign owners, monitor impacts, and align schedules.
Memory Hook: Dependencies = coordination + control.
Trigger Words: “handoffs,” “inter-team dependencies”

✅ FLASHCARD 13

Front: What tools help identify dependencies?
Back: Network diagrams, dependency logs, integrated schedule.
Memory Hook: Visualize to identify.
Trigger Words: “sequence,” “connections”

❇️ FLASHCARD 14

Front: What causes dependency-related project delays?
Back: Poor communication, unclear ownership, or unrealistic sequencing.
Memory Hook: Unowned dependency = delay.
Trigger Words: “handoff missed,” “blocked progress”

#### 🔹 INTEGRATED CHANGE CONTROL (PMI MUST-KNOW)

❇️ FLASHCARD 15

Front: What is Integrated Change Control?
Back: A framework for evaluating and approving changes across the entire project.
Memory Hook: One change affects many areas.
Trigger Words: “approval,” “impact analysis”

❇️ FLASHCARD 16

Front: What is the correct change sequence?
Back: Identify → Document → Analyze → Approve/Reject (CCB) → Update Plans → Communicate.
Memory Hook: Never act before analysis.
Trigger Words: “change request,” “baseline updates”

❇️ FLASHCARD 17

Front: Who approves updates to the project management plan?
Back: Change Control Board (CCB) or authorized sponsor.
Memory Hook: CCB = authority gate.
Trigger Words: “baseline change,” “formal approval”

#### 🔹 INTEGRATION TOOLS & TECHNIQUES

❇️ FLASHCARD 18

Front: What is the project charter’s role in integration?
Back: Provides high-level direction that all plans must align with.
Memory Hook: Charter = alignment anchor.
Trigger Words: “project authorization,” “high-level scope”

❇️ FLASHCARD 19

Front: What is configuration management?
Back: Identifying, controlling, tracking, and validating changes to documents or deliverables.
Memory Hook: Version control in project management.
Trigger Words: “document control,” “baseline tracking”

❇️ FLASHCARD 20

Front: What is the PMIS (Project Management Information System)?
Back: Software and tools that support planning, tracking, collaboration, and reporting.
Memory Hook: PMIS = digital integration engine.
Trigger Words: “project software,” “dashboard,” “tracking tool”

#### 🔹 AGILE / HYBRID INTEGRATION

❇️ FLASHCARD 21

Front: How is planning integrated in Agile?
Back: Through backlog refinement, iteration planning, and continuous feedback.
Memory Hook: Agile = rolling wave every sprint.
Trigger Words: “backlog,” “iteration,” “inspect & adapt”

❇️ FLASHCARD 22

Front: How is hybrid planning managed?
Back: Combine predictive baselines for stable work with Agile cycles for evolving work.
Memory Hook: Hybrid = predictable core + adaptive edges.
Trigger Words: “mixed method,” “dual planning”

❇️ FLASHCARD 23

Front: What should PM do when Agile teams conflict with predictive teams on timelines?
Back: Facilitate integration meetings and align dependencies and delivery cadence.
Memory Hook: Bridge Agile↔Predictive gaps.
Trigger Words: “cadence conflict,” “integration risk”

#### 🔹 TROUBLESHOOTING INTEGRATION ISSUES (PMI EXAM LOGIC)

❇️ FLASHCARD 24

Front: What should PM do when plans contain contradictory assumptions?
Back: Facilitate alignment session to reconcile and standardize assumptions.
Memory Hook: Correct contradictions early.
Trigger Words: “inconsistent assumptions,” “misalignment”

❇️ FLASHCARD 25

Front: What is the PM’s response when stakeholders pressure the team to skip planning?
Back: Push back and explain risks of poor planning and misalignment.
Memory Hook: Rushed planning = guaranteed rework.
Trigger Words: “skip planning,” “jump to execution”

### 📘 DOMAIN II — SECTION 10 (TASK 17) COMPLETE FLASHCARD SET

#### 🔹 CHANGE CONTROL FOUNDATIONS

✅ FLASHCARD 1

Front: What is the purpose of change control?
Back: To manage, evaluate, and approve changes in a structured and controlled way.
Memory Hook: Uncontrolled change = chaos.
Trigger Words: “change request,” “formal process”

✅ FLASHCARD 2

Front: What triggers a change request?
Back: Defects, stakeholder requests, risk events, scope changes, variance.
Memory Hook: Change always starts with a trigger.
Trigger Words: “new requirement,” “deviation,” “problem found”

#### 🔹 CHANGE CONTROL PROCESS

✅ FLASHCARD 3

Front: What is the correct change control sequence?
Back: Identify → Document → Analyze Impact → Submit to CCB → Approve/Reject → Update Baselines → Communicate.
Memory Hook: Never skip impact analysis.
Trigger Words: “process,” “step-by-step”

✅ FLASHCARD 4

Front: What is the PM’s first step when a stakeholder requests a change?
Back: Document the request and begin impact analysis.
Memory Hook: Write first, assess second.
Trigger Words: “new request,” “change asked”

❇️ FLASHCARD 5

Front: Who approves changes to baselines?
Back: Change Control Board (CCB) or authorized sponsor.
Memory Hook: CCB = gatekeeper.
Trigger Words: “approval authority,” “baseline change”

#### 🔹 IMPACT ANALYSIS

❇️ FLASHCARD 6

Front: What must be evaluated during impact analysis?
Back: Impact on scope, schedule, cost, quality, risk, resources, procurement.
Memory Hook: Impact all areas, not just one.
Trigger Words: “cross-impact,” “ripple effect”

❇️ FLASHCARD 7

Front: What should PM do if change benefits outweigh costs?
Back: Recommend approval with documented justification.
Memory Hook: Positive value → support change.
Trigger Words: “value add,” “enhancement”

❇️ FLASHCARD 8

Front: What should PM do if change is harmful or unnecessary?
Back: Recommend rejection and communicate rationale.
Memory Hook: Reject wasteful change.
Trigger Words: “no value,” “high risk”

#### 🔹 CHANGE DOCUMENTATION & COMMUNICATION

❇️ FLASHCARD 9

Front: What documents must be updated after change approval?
Back: Baselines, project management plan, subsidiary plans, registers, and reports.
Memory Hook: Approval → update everything affected.
Trigger Words: “plan updates,” “baseline shift”

❇️ FLASHCARD 10

Front: What is the PM’s role in communicating changes?
Back: Ensure all stakeholders understand impacts and updated responsibilities.
Memory Hook: Communicate to align.
Trigger Words: “notify stakeholders,” “communication plan”

#### 🔹 CONFIGURATION MANAGEMENT

❇️ FLASHCARD 11

Front: What is configuration management?
Back: Process for identifying, controlling, tracking, and auditing versions of project documents/deliverables.
Memory Hook: Version control for project artifacts.
Trigger Words: “document versioning,” “change tracking”

❇️ FLASHCARD 12

Front: What is a configuration item?
Back: Any document, deliverable, or component that is subject to version control.
Memory Hook: If it changes, it needs configuration control.
Trigger Words: “controlled item,” “baseline artifacts”

❇️ FLASHCARD 13

Front: What is the difference between change control and configuration control?
Back: Change control = approving changes; configuration control = managing versions.
Memory Hook: Approve vs track.
Trigger Words: “version,” “baseline,” “approval”

#### 🔹 PREVENTING UNCONTROLLED CHANGES

❇️ FLASHCARD 14

Front: What is scope creep?
Back: Unauthorized change to scope without formal approval.
Memory Hook: Creep = sneaky change.
Trigger Words: “just add this,” “no approval”

❇️ FLASHCARD 15

Front: What should PM do when team implements changes without approval?
Back: Stop work immediately, enforce process, and review with CCB.
Memory Hook: Unapproved = stop now.
Trigger Words: “gold plating,” “unauthorized changes”

#### 🔹 MANAGING MULTIPLE CHANGE REQUESTS

❇️ FLASHCARD 16

Front: How should PM prioritize multiple changes?
Back: Evaluate impact, urgency, risk, and alignment with strategic goals.
Memory Hook: Impact + value = priority.
Trigger Words: “prioritize,” “multiple changes”

❇️ FLASHCARD 17

Front: What must PM do when change requests contradict each other?
Back: Facilitate negotiation and alignment among stakeholders.
Memory Hook: Resolve conflicts before approval.
Trigger Words: “conflicting changes,” “negotiation”

❇️ FLASHCARD 18

Front: What should PM do when accumulated changes threaten baseline stability?
Back: Re-baseline only with CCB approval and justification.
Memory Hook: Big impact = re-baseline.
Trigger Words: “major deviation,” “new baseline”

#### 🔹 AGILE & ADAPTIVE CHANGE MANAGEMENT

❇️ FLASHCARD 19

Front: How is change managed in Agile?
Back: Change is expected; captured in backlog and prioritized by Product Owner.
Memory Hook: Agile = embrace change.
Trigger Words: “backlog,” “refinement,” “customer feedback”

❇️ FLASHCARD 20

Front: What happens to change requests during an active Agile sprint?
Back: They are logged and deferred until next sprint unless critical.
Memory Hook: No mid-sprint scope change.
Trigger Words: “sprint boundary,” “freeze scope”

❇️ FLASHCARD 21

Front: What should PM do when hybrid project receives change requests?
Back: Apply predictive change control to fixed components + Agile backlog for flexible components.
Memory Hook: Hybrid = dual handling.
Trigger Words: “mixed approach,” “hybrid governance”

#### 🔹 CHANGE MANAGEMENT TROUBLESHOOTING (PMI EXAM LOGIC)

❇️ FLASHCARD 22

Front: What should PM do when sponsor tries to bypass CCB?
Back: Respect the governance process and require formal review.
Memory Hook: No shortcuts—even for sponsor.
Trigger Words: “executive override,” “policy”

❇️ FLASHCARD 23

Front: What should PM do when customer insists on urgent change?
Back: Begin impact analysis immediately but still follow formal approval.
Memory Hook: Urgent ≠ skip process.
Trigger Words: “urgent change,” “rush request”

❇️ FLASHCARD 24

Front: How should PM handle repeated changes from the same stakeholder?
Back: Review root cause—unclear requirements, poor communication, or planning gaps.
Memory Hook: Solve the cause, not just the symptoms.
Trigger Words: “frequent changes,” “repeated requests”

### 📘 DOMAIN II — SECTION 11 (TASK 18) COMPLETE FLASHCARD SET

#### 🔹 PROCUREMENT FUNDAMENTALS

✅ FLASHCARD 1

Front: What is procurement management?
Back: Process of acquiring goods/services from outside the organization.
Memory Hook: Buy vs build decisions.
Trigger Words: “external vendor,” “acquisition”

✅ FLASHCARD 2

Front: What is the first step in procurement planning?
Back: Conduct make-or-buy analysis.
Memory Hook: Decide internal vs external first.
Trigger Words: “outsource,” “internal capability”

#### 🔹 PROCUREMENT PLANNING

❇️ FLASHCARD 3

Front: What is included in the Procurement Management Plan?
Back: Procurement strategy, contract types, timelines, vendor selection process, roles & responsibilities.
Memory Hook: Plan how to buy + from whom + when.
Trigger Words: “procurement approach,” “strategy”

❇️ FLASHCARD 4

Front: What should PM do when procurement affects schedule?
Back: Align procurement lead times with schedule baseline and adjust dependencies.
Memory Hook: Procurement delay = schedule delay.
Trigger Words: “lead time,” “long delivery”

#### 🔹 CONTRACT TYPES (EXAM MUST KNOW)

❇️ FLASHCARD 5

Front: What is a Fixed-Price (FP) contract?
Back: Vendor delivers for a set price; highest risk to seller.
Memory Hook: Fixed price = buyer safety.
Trigger Words: “cost certainty,” “seller risk”

❇️ FLASHCARD 6

Front: What is a Cost-Reimbursable (CR) contract?
Back: Buyer pays actual costs + fee; highest risk to buyer.
Memory Hook: Buyers pay more if cost grows.
Trigger Words: “uncertain scope,” “flexible cost”

❇️ FLASHCARD 7

Front: What is a Time and Materials (T&M) contract?
Back: Hybrid contract where buyer pays hourly/day rate; moderate risk.
Memory Hook: Time-based = open-ended cost.
Trigger Words: “consultants,” “services,” “rate card”

❇️ FLASHCARD 8

Front: When to use FP contracts?
Back: When scope is well-defined and stable.
Memory Hook: Clear scope = fixed price.
Trigger Words: “predictable work”

❇️ FLASHCARD 9

Front: When to use CR contracts?
Back: When scope is uncertain or research-based.
Memory Hook: Unknown scope = cost reimbursable.
Trigger Words: “R&D,” “uncertainty”

#### 🔹 PROCUREMENT DOCUMENTATION

❇️ FLASHCARD 10

Front: What is an RFP?
Back: Request for Proposal—used when seeking solutions and expertise from vendors.
Memory Hook: Proposal = solution.
Trigger Words: “vendor proposal,” “solution options”

❇️ FLASHCARD 11

Front: What is an RFQ?
Back: Request for Quotation—used for pricing information on well-defined items.
Memory Hook: Quote = price-focused.
Trigger Words: “price,” “commodity purchase”

❇️ FLASHCARD 12

Front: What is an SOW (Statement of Work)?
Back: Detailed description of products/services to be delivered by vendor.
Memory Hook: SOW = vendor’s scope.
Trigger Words: “deliverables,” “scope clarity”

#### 🔹 VENDOR SELECTION

❇️ FLASHCARD 13

Front: What is the purpose of source selection criteria?
Back: Define how proposals will be evaluated—cost, quality, capability, experience.
Memory Hook: Criteria = objective comparison.
Trigger Words: “scoring,” “vendor evaluation”

❇️ FLASHCARD 14

Front: What is a bidder conference?
Back: Meeting to ensure all vendors understand requirements equally.
Memory Hook: Level playing field.
Trigger Words: “clarification,” “vendor questions”

❇️ FLASHCARD 15

Front: What should PM do when proposals vary widely?
Back: Re-examine requirements clarity and update documentation if needed.
Memory Hook: Wide variance = unclear scope.
Trigger Words: “bids mismatch,” “spec unclear”

#### 🔹 CONTRACT ADMINISTRATION

❇️ FLASHCARD 16

Front: What is contract administration?
Back: Monitoring vendor performance, managing relationships, enforcing contract terms.
Memory Hook: Manage vendor like part of team.
Trigger Words: “performance,” “compliance”

❇️ FLASHCARD 17

Front: What should PM do when vendor performance declines?
Back: Review contract terms, issue corrective action, escalate per agreement.
Memory Hook: Contract = enforcement tool.
Trigger Words: “non-performance,” “corrective action”

❇️ FLASHCARD 18

Front: What is a procurement audit?
Back: Examines procurement processes and performance for improvements.
Memory Hook: Audit = lessons learned for buying.
Trigger Words: “process review,” “improvement”

#### 🔹 CLAIMS & DISPUTE MANAGEMENT

❇️ FLASHCARD 19

Front: What are procurement claims?
Back: Requests for compensation due to contract disagreements or unmet obligations.
Memory Hook: Claims = conflict over contract terms.
Trigger Words: “dispute,” “contractual rights”

❇️ FLASHCARD 20

Front: What is alternative dispute resolution (ADR)?
Back: Non-legal methods (mediation, arbitration) to resolve disputes.
Memory Hook: ADR = avoid court.
Trigger Words: “conflict resolution,” “vendor dispute”

❇️ FLASHCARD 21

Front: What should PM do when vendor files a claim?
Back: Follow contract procedures, document everything, escalate to legal/procurement.
Memory Hook: Follow the contract rules.
Trigger Words: “formal claim,” “documentation”

#### 🔹 CONTRACT CLOSURE & HANDOVER

❇️ FLASHCARD 22

Front: What is procurement closure?
Back: Confirm all work delivered, finalize payments, close contract, update records.
Memory Hook: Close contract before project close.
Trigger Words: “finalization,” “vendor offboarding”

❇️ FLASHCARD 23

Front: What must PM ensure before closing a contract?
Back: All deliverables accepted, issues resolved, documentation archived.
Memory Hook: No loose ends.
Trigger Words: “acceptance,” “closure criteria”

#### 🔹 AGILE & HYBRID PROCUREMENT

❇️ FLASHCARD 24

Front: How does procurement work in Agile projects?
Back: Contracts emphasize collaboration, flexibility, and incremental delivery.
Memory Hook: Agile = adaptable contracts.
Trigger Words: “collaboration,” “value delivery”

❇️ FLASHCARD 25

Front: What contract type aligns best with Agile?
Back: Time & Materials with not-to-exceed caps or incremental fixed-price contracts.
Memory Hook: Flexible structure with guardrails.
Trigger Words: “iterative,” “variable scope”

❇️ FLASHCARD 26

Front: What is PM’s role in hybrid procurement?
Back: Balance predictive cost control with agile flexibility and continuous vendor engagement.
Memory Hook: Hybrid = structure + adaptability.
Trigger Words: “mixed approach,” “dual governance”

### 📘 DOMAIN II — SECTION 12 (TASK 19) COMPLETE FLASHCARD SET

#### 🔹 ARTIFACT MANAGEMENT BASICS

✅ FLASHCARD 1

Front: What are project artifacts?
Back: Documents, records, deliverables, logs, and reports generated throughout the project.
Memory Hook: Artifacts = project evidence.
Trigger Words: “documents,” “records,” “outputs”

✅ FLASHCARD 2

Front: What is the first step in managing project artifacts?
Back: Identify which artifacts are needed based on project methodology and stakeholder needs.
Memory Hook: Identify before organizing.
Trigger Words: “artifact list,” “document requirements”

#### 🔹 ARTIFACT ORGANIZATION & STORAGE

❇️ FLASHCARD 3

Front: What is an artifact repository?
Back: A centralized system (SharePoint, Confluence, PMIS) for storing and organizing documents.
Memory Hook: One source of truth.
Trigger Words: “document storage,” “centralized access”

❇️ FLASHCARD 4

Front: Why centralize storage?
Back: Ensures version control, accessibility, security, and consistency.
Memory Hook: One place = no confusion.
Trigger Words: “organized,” “single location”

#### 🔹 VERSION CONTROL & CONFIGURATION MANAGEMENT

❇️ FLASHCARD 5

Front: What is version control?
Back: Process of tracking revisions and ensuring users access correct document versions.
Memory Hook: No confusion about versions.
Trigger Words: “v1, v2,” “revision history”

❇️ FLASHCARD 6

Front: What is configuration management?
Back: Identification, control, tracking, and auditing of artifact changes.
Memory Hook: Track everything that changes.
Trigger Words: “change tracking,” “artifact control”

❇️ FLASHCARD 7

Front: What is a configuration item?
Back: Any artifact or deliverable under version or change control.
Memory Hook: If it changes → track it.
Trigger Words: “controlled item,” “document version”

#### 🔹 ACCESS CONTROL & SECURITY

❇️ FLASHCARD 8

Front: What is access control?
Back: Managing user permissions to view, edit, or approve artifacts.
Memory Hook: Right access = security.
Trigger Words: “permissions,” “security roles”

❇️ FLASHCARD 9

Front: What should PM do when sensitive artifacts are shared improperly?
Back: Restrict access, review permissions, retrain team on data handling procedures.
Memory Hook: Control access breaches immediately.
Trigger Words: “file leak,” “misuse”

#### 🔹 ARTIFACT TYPES & USES

❇️ FLASHCARD 10

Front: What are examples of key project artifacts?
Back: Charter, WBS, schedule, budget, risk register, issue log, change log, status reports.
Memory Hook: Artifacts = all major PM outputs.
Trigger Words: “documentation,” “project records”

❇️ FLASHCARD 11

Front: What is the purpose of the issue log?
Back: Track project issues, owners, status, and resolution.
Memory Hook: Issues = must resolve.
Trigger Words: “problem tracking,” “open items”

❇️ FLASHCARD 12

Front: What is the purpose of the lessons learned register?
Back: Capture insights, successes, challenges, and recommendations for future projects.
Memory Hook: Learn as you go.
Trigger Words: “continuous improvement,” “knowledge capture”

❇️ FLASHCARD 13

Front: What is the change log?
Back: Document that records all change requests and their approval status.
Memory Hook: Every change accounted for.
Trigger Words: “change tracking,” “approvals”

❇️ FLASHCARD 14

Front: What is the risk register?
Back: Document listing risks, triggers, owners, responses, and status.
Memory Hook: Risk database.
Trigger Words: “risk management,” “probability,” “impact”

#### 🔹 ARTIFACT QUALITY & COMPLETENESS

❇️ FLASHCARD 15

Front: How does PM ensure artifact accuracy?
Back: Review regularly, validate with stakeholders, and update promptly.
Memory Hook: Validate and refresh often.
Trigger Words: “accuracy,” “updates needed”

❇️ FLASHCARD 16

Front: What should PM do if artifact data is outdated?
Back: Update immediately and communicate changes to the team.
Memory Hook: Outdated = unreliable.
Trigger Words: “stale data,” “missing updates”

#### 🔹 ARTIFACT RETENTION & ARCHIVING

❇️ FLASHCARD 17

Front: What is the purpose of archiving?
Back: Preserve project history for compliance, audit, and reuse.
Memory Hook: Archive = organizational memory.
Trigger Words: “storage,” “historic record”

❇️ FLASHCARD 18

Front: What should PM do before archiving documents?
Back: Ensure all deliverables accepted, approvals complete, and documents finalized.
Memory Hook: Finalize then archive.
Trigger Words: “completed project,” “record retention”

❇️ FLASHCARD 19

Front: How long should artifacts be retained?
Back: According to organizational policies, regulatory requirements, or contract terms.
Memory Hook: Follow retention rules.
Trigger Words: “compliance,” “legal requirement”

#### 🔹 COMMUNICATION & ACCESSIBILITY

❇️ FLASHCARD 20

Front: What should PM do to maximize artifact accessibility?
Back: Use naming conventions, folder structure, metadata, and consistent formats.
Memory Hook: Standardize = easy to find.
Trigger Words: “organization,” “naming standards”

❇️ FLASHCARD 21

Front: How should PM share updates to artifacts?
Back: Communicate through defined channels and update version history.
Memory Hook: Notify + update records.
Trigger Words: “new version,” “document updates”

#### 🔹 AGILE/HYBRID ARTIFACT MANAGEMENT

❇️ FLASHCARD 22

Front: What artifacts are emphasized in Agile?
Back: Backlog, Definition of Done, user stories, burn charts, working product increments.
Memory Hook: Agile = lightweight but essential.
Trigger Words: “backlog,” “increment,” “DoD”

❇️ FLASHCARD 23

Front: How is documentation handled in Agile?
Back: Just enough documentation for value delivery and knowledge sharing.
Memory Hook: Minimal but meaningful.
Trigger Words: “light documentation,” “team shared”

❇️ FLASHCARD 24

Front: What is the PM’s role in hybrid artifact management?
Back: Balance predictive documentation (formal) with Agile documentation (lightweight).
Memory Hook: Hybrid = flexibility + compliance.
Trigger Words: “mixed project,” “dual documentation”

#### 🔹 TROUBLESHOOTING ARTIFACT ISSUES (PMI LOGIC)

❇️ FLASHCARD 25

Front: What should PM do when team members use outdated versions?
Back: Reinforce version control rules, restrict old versions, and retrain team.
Memory Hook: Old versions = chaos.
Trigger Words: “wrong file,” “confusion”

❇️ FLASHCARD 26

Front: What should PM do when stakeholders complain artifacts are hard to find?
Back: Reorganize repository, simplify structure, improve naming conventions.
Memory Hook: Ease of access = better engagement.
Trigger Words: “misplaced,” “hard to locate”

### 📘 DOMAIN II — SECTION 13 (TASK 20) COMPLETE FLASHCARD SET

#### 🔹 METHODOLOGY SELECTION FOUNDATIONS

✅ FLASHCARD 1

Front: What is the purpose of methodology selection?
Back: To determine the best approach to deliver project value based on constraints, uncertainty, and stakeholder needs.
Memory Hook: Choose the right way to work.
Trigger Words: “approach,” “fit for purpose”

❇️ FLASHCARD 2

Front: What should PM evaluate before choosing a methodology?
Back: Requirements clarity, complexity, volatility, team experience, stakeholder involvement.
Memory Hook: Clarity, Complexity, Change, Capability.
Trigger Words: “uncertainty,” “team maturity”

#### 🔹 PREDICTIVE (WATERFALL) INDICATORS

❇️ FLASHCARD 3

Front: When is predictive methodology best?
Back: When scope is stable, requirements well-defined, and changes low.
Memory Hook: Stable = predictive.
Trigger Words: “fixed scope,” “low change,” “detailed upfront”

❇️ FLASHCARD 4

Front: When does WBS replace backlog?
Back: When deliverables can be fully decomposed upfront.
Memory Hook: Clear deliverables = WBS works.
Trigger Words: “fully defined,” “no iterations needed”

#### 🔹 AGILE / ADAPTIVE INDICATORS

❇️ FLASHCARD 5

Front: When is Agile best?
Back: When requirements change frequently, customer involvement is high, and increments deliver value.
Memory Hook: Change-friendly approach.
Trigger Words: “iterative,” “customer collaboration”

❇️ FLASHCARD 6

Front: What is the Agile mindset?
Back: Focus on collaboration, flexibility, continuous feedback, incremental value.
Memory Hook: Respond over plan.
Trigger Words: “adaptive,” “feedback-driven”

❇️ FLASHCARD 7

Front: When is Agile risky?
Back: When stakeholders are unavailable or regulatory constraints require strict documentation.
Memory Hook: Agile fails without engagement.
Trigger Words: “heavy governance,” “compliance”

#### 🔹 HYBRID APPROACH INDICATORS

❇️ FLASHCARD 8

Front: When is hybrid approach best?
Back: When parts of project are stable while others evolve.
Memory Hook: Stable core + adaptive edges.
Trigger Words: “mixed environment,” “partial uncertainty”

❇️ FLASHCARD 9

Front: What should PM do when team demands Agile but stakeholders demand predictability?
Back: Use hybrid—predictive planning + Agile execution for evolving portions.
Memory Hook: Balance flexibility and control.
Trigger Words: “compromise,” “dual approach”

#### 🔹 ORGANIZATIONAL FACTORS

❇️ FLASHCARD 10

Front: How do organizational culture and maturity influence methodology?
Back: High maturity supports Agile; low maturity or strict governance favors predictive.
Memory Hook: Culture determines pace.
Trigger Words: “org maturity,” “governance model”

❇️ FLASHCARD 11

Front: What should PM do if enterprise standards conflict with chosen methodology?
Back: Tailor method within constraints and obtain approvals.
Memory Hook: Customize but stay compliant.
Trigger Words: “organizational policies,” “tailoring”

#### 🔹 COMPLEXITY & UNCERTAINTY ASSESSMENT

❇️ FLASHCARD 12

Front: What drives methodology selection under uncertainty?
Back: Volatility of requirements, pace of change, and innovation level.
Memory Hook: Uncertainty → iterative approach.
Trigger Words: “changing needs,” “innovation”

❇️ FLASHCARD 13

Front: What should PM do when unsure if requirements will change?
Back: Choose adaptive or hybrid to enable flexibility.
Memory Hook: When in doubt, stay adaptive.
Trigger Words: “uncertainty,” “unknowns”

#### 🔹 TAILORING THE APPROACH

❇️ FLASHCARD 14

Front: What is tailoring?
Back: Customizing methodology based on the project environment, team, and constraints.
Memory Hook: No one-size-fits-all.
Trigger Words: “adapt method,” “custom approach”

❇️ FLASHCARD 15

Front: What should PM tailor?
Back: Processes, tools, documentation, cadence, governance levels.
Memory Hook: Tailor process, not principles.
Trigger Words: “fit project context,” “optimize”

❇️ FLASHCARD 16

Front: What is a tailoring decision log?
Back: Document explaining tailoring choices, rationale, and expected impacts.
Memory Hook: Document why you tailor.
Trigger Words: “decision record,” “customization”

#### 🔹 GOVERNANCE IMPLICATIONS

❇️ FLASHCARD 17

Front: How does methodology affect governance?
Back: Predictive = formal reviews; Agile = frequent informal reviews and demos.
Memory Hook: Governance follows cadence.
Trigger Words: “oversight,” “review cycles”

❇️ FLASHCARD 18

Front: What should PM do when governance board wants more updates?
Back: Increase reporting frequency, regardless of method used.
Memory Hook: Governance needs override.
Trigger Words: “reporting,” “oversight changes”

#### 🔹 TEAM CAPABILITY & MATURITY

❇️ FLASHCARD 19

Front: What affects method selection based on team characteristics?
Back: Team experience, cross-functionality, collaboration capability, autonomy.
Memory Hook: Team capability = method viability.
Trigger Words: “experience,” “skillset”

❇️ FLASHCARD 20

Front: What should PM do if team is unfamiliar with Agile?
Back: Provide training, coaching, and transition gradually (hybrid helps).
Memory Hook: Ramp up skill before full Agile.
Trigger Words: “training needed,” “new to Agile”

#### 🔹 STAKEHOLDER ENGAGEMENT IMPACT

❇️ FLASHCARD 21

Front: When stakeholders require frequent feedback?
Back: Use Agile or hybrid to provide iterative visibility.
Memory Hook: Frequent feedback → Agile.
Trigger Words: “short cycles,” “demo”

❇️ FLASHCARD 22

Front: What to do when stakeholders avoid involvement?
Back: Use predictive approach with clear upfront requirements and approvals.
Memory Hook: Low engagement → predictive.
Trigger Words: “absent stakeholders,” “low interaction”

#### 🔹 TOOL & TECHNOLOGY INFLUENCE

❇️ FLASHCARD 23

Front: How does technology stability influence method?
Back: Stable technology → predictive; emerging tech → Agile/hybrid.
Memory Hook: New tech → iterative learning.
Trigger Words: “innovation,” “uncertainty”

❇️ FLASHCARD 24

Front: What should PM do when using new tools?
Back: Adopt iterative cycles for testing, learning, and adapting.
Memory Hook: Experiment → refine.
Trigger Words: “pilot,” “proof of concept”

#### 🔹 EXAM TROUBLESHOOTING (PMI LOGIC)

❇️ FLASHCARD 25

Front: What should PM do if chosen methodology is failing mid-project?
Back: Reassess and re-tailor the methodology—even midstream if needed.
Memory Hook: Course-correct early.
Trigger Words: “method not working,” “pivot”

❇️ FLASHCARD 26

Front: What should PM do when executives demand a fixed date but requirements are unclear?
Back: Use hybrid—predictive scheduling with Agile requirement development.
Memory Hook: Fixed deadline + unclear scope = hybrid.
Trigger Words: “deadline,” “unclear requirements”

### 📘 DOMAIN II — SECTION 14 (TASK 21) COMPLETE FLASHCARD SET

#### 🔹 GOVERNANCE FOUNDATIONS

✅ FLASHCARD 1

Front: What is project governance?
Back: Framework that defines decision-making authority, policies, procedures, and oversight for the project.
Memory Hook: Governance = how decisions get made.
Trigger Words: “authority,” “oversight,” “structure”

✅ FLASHCARD 2

Front: What is the PM’s role in governance?
Back: Implement governance processes, ensure compliance, and escalate issues as required.
Memory Hook: PM executes governance; does not define it.
Trigger Words: “compliance,” “escalation”

#### 🔹 GOVERNANCE COMPONENTS

❇️ FLASHCARD 3

Front: What are the key elements of governance?
Back: Decision rights, roles/responsibilities, escalation paths, control processes, reporting cadences.
Memory Hook: Governance = roles + rules.
Trigger Words: “decision authority,” “procedures”

❇️ FLASHCARD 4

Front: What is a governance plan?
Back: Document that describes how governance will be applied, including review cycles and escalation routes.
Memory Hook: Plan how to govern.
Trigger Words: “governance model,” “control framework”

❇️ FLASHCARD 5

Front: What is the role of a steering committee?
Back: Provide strategic direction, approve major decisions, resolve escalations, remove barriers.
Memory Hook: Steering = strategic decisions.
Trigger Words: “executive oversight,” “escalation body”

#### 🔹 ROLES & RESPONSIBILITIES

❇️ FLASHCARD 6

Front: Who owns project vision and direction?
Back: The project sponsor.
Memory Hook: Sponsor = vision + authority.
Trigger Words: “funding,” “executive owner”

❇️ FLASHCARD 7

Front: What is the PM accountable for?
Back: Delivering project objectives within governance constraints.
Memory Hook: PM delivers within rules.
Trigger Words: “delivery,” “compliance”

❇️ FLASHCARD 8

Front: What is the team responsible for?
Back: Executing tasks, producing deliverables, following standards.
Memory Hook: Team builds under PM direction.
Trigger Words: “execution,” “delivery team”

#### 🔹 DECISION-MAKING FRAMEWORKS

❇️ FLASHCARD 9

Front: What should PM do when decision-making authority is unclear?
Back: Clarify roles, escalate to sponsor if needed, document decision rights.
Memory Hook: Ambiguity = resolve early.
Trigger Words: “unclear authority,” “role conflict”

❇️ FLASHCARD 10

Front: What is a RACI matrix used for?
Back: Defines roles and responsibilities (Responsible, Accountable, Consulted, Informed).
Memory Hook: RACI = who does what.
Trigger Words: “responsibility charting,” “clarity”

#### 🔹 ESCALATION PATHS

❇️ FLASHCARD 11

Front: What is an escalation path?
Back: Defined sequence for escalating issues, decisions, and risks.
Memory Hook: Clear path prevents bottlenecks.
Trigger Words: “issue escalation,” “decision block”

❇️ FLASHCARD 12

Front: When should PM escalate?
Back: When issue exceeds authority or negatively impacts project goals.
Memory Hook: Escalate beyond authority limits.
Trigger Words: “beyond PM control,” “critical impact”

❇️ FLASHCARD 13

Front: What should PM do before escalating?
Back: Attempt to resolve through collaboration and data-driven discussion.
Memory Hook: Resolve first, escalate last.
Trigger Words: “conflict,” “impasse”

#### 🔹 GOVERNANCE STRUCTURES & ORGANIZATIONAL MODELS

❇️ FLASHCARD 14

Front: What are the three primary organizational structures?
Back: Functional, Matrix (weak/balanced/strong), and Projectized.
Memory Hook: F-M-P.
Trigger Words: “organizational structure,” “authority levels”

❇️ FLASHCARD 15

Front: Who has the most authority in a functional organization?
Back: Functional manager.
Memory Hook: Functional = manager rules.
Trigger Words: “low PM authority”

❇️ FLASHCARD 16

Front: Who has the most authority in a projectized organization?
Back: Project manager.
Memory Hook: Projectized = PM power.
Trigger Words: “full authority,” “dedicated team”

❇️ FLASHCARD 17

Front: What is characteristic of a matrix organization?
Back: Shared authority between functional managers and PMs.
Memory Hook: Matrix = dual reporting.
Trigger Words: “shared authority,” “resource negotiation”

#### 🔹 GOVERNANCE OVERSIGHT & CONTROLS

❇️ FLASHCARD 18

Front: What is phase gate review?
Back: Formal checkpoint at transition between phases to assess readiness and performance.
Memory Hook: Gate = go/no-go decision.
Trigger Words: “stage review,” “go/no-go”

❇️ FLASHCARD 19

Front: What should PM prepare for phase gate review?
Back: Completed deliverables, metrics, risks, issues, updated forecasts.
Memory Hook: Gate = evidence + status.
Trigger Words: “status review,” “decision meeting”

❇️ FLASHCARD 20

Front: What is governance compliance?
Back: Following required policies, documentation standards, and controls.
Memory Hook: Follow the rules.
Trigger Words: “audit,” “regulatory adherence”

#### 🔹 GOVERNANCE IN AGILE / HYBRID

❇️ FLASHCARD 21

Front: How is governance handled in Agile?
Back: Frequent reviews, demonstration of increments, transparent metrics.
Memory Hook: Visibility every iteration.
Trigger Words: “demo,” “inspect & adapt”

❇️ FLASHCARD 22

Front: Who governs Agile prioritization?
Back: Product Owner (value-based decisions).
Memory Hook: PO = priority authority.
Trigger Words: “backlog,” “value rank”

❇️ FLASHCARD 23

Front: How does hybrid governance operate?
Back: Predictive governance for fixed elements + Agile cadence for evolving work.
Memory Hook: Hybrid = combined oversight.
Trigger Words: “dual governance,” “mixed method”

#### 🔹 TROUBLESHOOTING GOVERNANCE ISSUES (PMI EXAM LOGIC)

❇️ FLASHCARD 24

Front: What should PM do when governance requirements conflict with project needs?
Back: Discuss with sponsor and propose tailored adjustments while maintaining compliance.
Memory Hook: Adapt within boundaries.
Trigger Words: “governance conflict,” “tailoring”

❇️ FLASHCARD 25

Front: What should PM do when leadership bypasses governance process?
Back: Reinforce governance framework and escalate if needed.
Memory Hook: Governance applies to everyone.
Trigger Words: “policy violation,” “executive override”

### 📘 DOMAIN II — SECTION 15 (TASK 22) COMPLETE FLASHCARD SET

#### 🔹 ISSUE MANAGEMENT FOUNDATIONS

✅ FLASHCARD 1

Front: What is a project issue?
Back: A current problem or obstacle that has already occurred and requires immediate action.
Memory Hook: Issue = now, risk = future.
Trigger Words: “problem,” “has occurred,” “urgent”

✅ FLASHCARD 2

Front: What is the first step when an issue arises?
Back: Document it in the issue log with owner and due date.
Memory Hook: Log → assign → act.
Trigger Words: “new issue,” “unexpected problem”

#### 🔹 ISSUE LOG & TRACKING

❇️ FLASHCARD 3

Front: What information is tracked in the issue log?
Back: Description, owner, priority, impact, status, due date, resolution actions.
Memory Hook: Track who, what, when.
Trigger Words: “issue tracking,” “ownership”

❇️ FLASHCARD 4

Front: What is the PM’s responsibility for issue log?
Back: Ensure it is updated, reviewed regularly, and shared with stakeholders.
Memory Hook: PM owns the log.
Trigger Words: “review,” “update,” “communication”

#### 🔹 ASSESSMENT & PRIORITIZATION

❇️ FLASHCARD 5

Front: What determines issue priority?
Back: Severity of impact + urgency of required action.
Memory Hook: Impact + urgency = priority.
Trigger Words: “high priority,” “critical issue”

❇️ FLASHCARD 6

Front: What should PM do when multiple issues occur simultaneously?
Back: Prioritize based on impact on scope, schedule, cost, quality, and risk.
Memory Hook: Impact governs order.
Trigger Words: “multiple issues,” “triage”

#### 🔹 ROOT CAUSE ANALYSIS & PROBLEM SOLVING

❇️ FLASHCARD 7

Front: What is root cause analysis?
Back: Identifying the underlying cause of an issue, not just symptoms.
Memory Hook: Fix the cause, not the symptom.
Trigger Words: “analysis,” “problem solving”

❇️ FLASHCARD 8

Front: What tools support root cause analysis?
Back: Fishbone diagram, 5 Whys, flowcharts.
Memory Hook: Ask why repeatedly.
Trigger Words: “defect cause,” “problem origin”

#### 🔹 ISSUE RESPONSE & ESCALATION

❇️ FLASHCARD 9

Front: What is the PM’s next step after issue analysis?
Back: Develop and implement an action plan for resolution.
Memory Hook: Analyze → plan → act.
Trigger Words: “corrective action,” “resolution”

❇️ FLASHCARD 10

Front: When should PM escalate an issue?
Back: When it exceeds PM authority or threatens project objectives.
Memory Hook: Beyond authority → escalate.
Trigger Words: “needs approval,” “critical impact”

❇️ FLASHCARD 11

Front: What should PM do before escalating?
Back: Attempt resolution within PM authority and provide data.
Memory Hook: Try first, escalate last.
Trigger Words: “impasse,” “authority limit”

#### 🔹 STAKEHOLDER COMMUNICATION

❇️ FLASHCARD 12

Front: What is the PM’s communication role during an issue?
Back: Inform stakeholders of impact, status, and planned resolution steps.
Memory Hook: Transparency builds trust.
Trigger Words: “update stakeholders,” “communication”

❇️ FLASHCARD 13

Front: What should PM do when stakeholders disagree on issue severity?
Back: Facilitate discussion, present objective data, and align expectations.
Memory Hook: Data resolves opinion.
Trigger Words: “conflicting views,” “misalignment”

#### 🔹 ISSUE MITIGATION & PREVENTION

❇️ FLASHCARD 14

Front: What is the difference between issue resolution and issue mitigation?
Back: Resolution fixes the current issue; mitigation prevents recurrence.
Memory Hook: Fix now + prevent next time.
Trigger Words: “preventive action,” “recurrence”

❇️ FLASHCARD 15

Front: What should PM do after issue resolution?
Back: Update logs, document lessons learned, adjust plans if needed.
Memory Hook: Close the loop.
Trigger Words: “record,” “improve,” “update registers”

#### 🔹 AGILE/HYBRID ISSUE MANAGEMENT

❇️ FLASHCARD 16

Front: How are issues handled in Agile teams?
Back: Addressed immediately in daily standups; assigned to team members.
Memory Hook: Agile = fast resolution.
Trigger Words: “standup,” “impediment”

❇️ FLASHCARD 17

Front: Who resolves impediments in Scrum?
Back: Scrum Master removes blockers to enable team flow.
Memory Hook: SM = impediment remover.
Trigger Words: “blockers,” “team support”

❇️ FLASHCARD 18

Front: How are issues documented in Agile?
Back: Often tracked on board cards, impediment lists, or team backlogs.
Memory Hook: Visible to everyone.
Trigger Words: “Kanban,” “scrum board”

#### 🔹 TROUBLESHOOTING PMI EXAM SCENARIOS

❇️ FLASHCARD 19

Front: What should PM do when team hides issues?
Back: Reinforce open communication environment and address root cause of fear.
Memory Hook: Silence = danger.
Trigger Words: “lack of transparency,” “hidden issues”

❇️ FLASHCARD 20

Front: What should PM do if an issue repeatedly reappears?
Back: Do deeper root cause analysis and implement preventive actions.
Memory Hook: Recurring = unresolved cause.
Trigger Words: “repeat issue,” “persistent problem”

❇️ FLASHCARD 21

Front: What should PM do when an issue impacts multiple teams?
Back: Facilitate cross-team alignment and assign a coordinated action owner.
Memory Hook: Shared issue = shared solution.
Trigger Words: “cross-functional,” “coordination”

#### 🔹 COMPLETION & DOCUMENTATION

❇️ FLASHCARD 22

Front: What does “issue resolved” truly mean?
Back: Root cause addressed, corrective action implemented, impacts documented.
Memory Hook: Resolved = fixed + documented.
Trigger Words: “resolution complete,” “closed issue”

❇️ FLASHCARD 23

Front: Why is the issue log important during closing?
Back: Confirms all issues are resolved or documented for transition.
Memory Hook: No open issues at closure.
Trigger Words: “closeout,” “handover”

### 📘 DOMAIN II — SECTION 16 (TASK 23) COMPLETE FLASHCARD SET

#### 🔹 KNOWLEDGE TRANSFER BASICS

✅ FLASHCARD 1

Front: What is knowledge transfer?
Back: The process of capturing, sharing, and transitioning critical project information to ensure continuity.
Memory Hook: Transfer knowledge, not just documents.
Trigger Words: “handover,” “sharing knowledge”

✅ FLASHCARD 2

Front: What is the first step in planning knowledge transfer?
Back: Identify what knowledge is critical for ongoing operations or future phases.
Memory Hook: Identify before capturing.
Trigger Words: “critical knowledge,” “dependencies”

#### 🔹 CAPTURING KNOWLEDGE

❇️ FLASHCARD 3

Front: What types of knowledge need to be transferred?
Back: Technical, process, stakeholder context, historical decisions, risks, lessons learned.
Memory Hook: What, how, who, why.
Trigger Words: “process knowledge,” “lessons,” “context”

❇️ FLASHCARD 4

Front: What tool helps capture lessons learned throughout the project?
Back: Lessons Learned Register.
Memory Hook: Record as you go.
Trigger Words: “lessons,” “improvement”

❇️ FLASHCARD 5

Front: What should PM do if team is not documenting lessons learned?
Back: Reinforce documentation expectations and integrate into project cadence (e.g., retrospectives).
Memory Hook: Capture continuously.
Trigger Words: “lack of documentation,” “team oversight”

#### 🔹 KNOWLEDGE TRANSFER METHODS

❇️ FLASHCARD 6

Front: What are effective knowledge transfer techniques?
Back: Workshops, shadowing, pair programming, training sessions, documentation reviews.
Memory Hook: Teach, show, observe, document.
Trigger Words: “training,” “handover sessions”

❇️ FLASHCARD 7

Front: What method ensures effective operational handover?
Back: Hands-on training with the receiving team, not just written materials.
Memory Hook: Practice beats reading.
Trigger Words: “operations,” “training”

❇️ FLASHCARD 8

Front: What should PM do when documentation alone is insufficient?
Back: Provide verbal walkthroughs and interactive sessions.
Memory Hook: Explain + demonstrate.
Trigger Words: “context missing,” “clarification”

#### 🔹 KNOWLEDGE TRANSFER OWNERSHIP

❇️ FLASHCARD 9

Front: Who is responsible for ensuring knowledge transfer is completed?
Back: The project manager.
Memory Hook: PM ensures continuity.
Trigger Words: “handover owner,” “responsibility”

❇️ FLASHCARD 10

Front: Who typically receives knowledge transfer?
Back: Operations, support teams, future project teams, or product owners.
Memory Hook: Recipients = keep the work running.
Trigger Words: “Ops,” “support,” “future phases”

❇️ FLASHCARD 11

Front: What should PM do if receiving team is unprepared?
Back: Assess readiness, adjust schedule, and provide additional training.
Memory Hook: Prepare recipients before transfer.
Trigger Words: “lack of readiness,” “unprepared team”

#### 🔹 TRANSITION & CONTINUITY PLANNING

❇️ FLASHCARD 12

Front: What is a transition plan?
Back: Document outlining how responsibilities, knowledge, and deliverables will move to receiving team.
Memory Hook: Plan the handoff.
Trigger Words: “transition,” “handover plan”

❇️ FLASHCARD 13

Front: What should PM include in a transition plan?
Back: Deliverables list, knowledge areas, training schedule, owner assignments, acceptance criteria.
Memory Hook: What + who + when + acceptance.
Trigger Words: “handover details,” “criteria”

❇️ FLASHCARD 14

Front: What is “knowledge continuity”?
Back: Keeping important information accessible and understood even after team changes.
Memory Hook: Continuity = retention across people.
Trigger Words: “turnover,” “team changes”

#### 🔹 VERIFYING KNOWLEDGE TRANSFER

❇️ FLASHCARD 15

Front: How does PM verify knowledge transfer is effective?
Back: Confirm recipient can perform tasks independently via demonstration or test runs.
Memory Hook: Verify through action.
Trigger Words: “confirmation,” “competency”

❇️ FLASHCARD 16

Front: What should PM do if the receiving team cannot execute tasks after KT?
Back: Provide additional training, revise materials, schedule more sessions.
Memory Hook: Teach until competent.
Trigger Words: “failure in KT,” “follow-up needed”

#### 🔹 COMMUNICATION & STAKEHOLDER ALIGNMENT

❇️ FLASHCARD 17

Front: How should PM communicate knowledge transfer progress?
Back: Provide regular updates to stakeholders with readiness status and gaps.
Memory Hook: Communicate progress + readiness.
Trigger Words: “status,” “handover clarity”

❇️ FLASHCARD 18

Front: What should PM do when stakeholders disagree on completion of KT?
Back: Use documented acceptance criteria and task demonstrations to clarify.
Memory Hook: Evidence resolves disputes.
Trigger Words: “acceptance,” “evaluation”

#### 🔹 AGILE/HYBRID KNOWLEDGE TRANSFER

❇️ FLASHCARD 19

Front: How is knowledge transfer embedded in Agile?
Back: Through continuous collaboration, daily standups, reviews, and backlog refinement.
Memory Hook: KT happens daily.
Trigger Words: “collaboration,” “iteration”

❇️ FLASHCARD 20

Front: What Agile artifact supports knowledge continuity?
Back: Definition of Done, which clarifies completion standards and team understanding.
Memory Hook: DoD = shared knowledge.
Trigger Words: “criteria,” “alignment”

❇️ FLASHCARD 21

Front: How is hybrid KT managed?
Back: Predictive documentation + Agile continuous communication.
Memory Hook: Hybrid = formal + informal.
Trigger Words: “mixed approach,” “documentation + collaboration”

#### 🔹 TROUBLESHOOTING PMI EXAM SCENARIOS

❇️ FLASHCARD 22

Front: What should PM do when key team member leaves mid-project?
Back: Initiate emergency knowledge transfer using shadowing and documentation review.
Memory Hook: Immediate KT prevents risk.
Trigger Words: “turnover,” “sudden exit”

❇️ FLASHCARD 23

Front: What should PM do when knowledge transfer is delayed?
Back: Escalate risk to sponsor, adjust schedule, and reallocate resources.
Memory Hook: Delay = risk escalation.
Trigger Words: “KT not happening,” “schedule risk”

❇️ FLASHCARD 24

Front: What should PM do when recipients reject KT materials or say they’re unclear?
Back: Revise documentation, simplify, add visual aids, perform live walkthroughs.
Memory Hook: Clarify until understood.
Trigger Words: “unclear documentation,” “feedback”

### 📘 DOMAIN II — SECTION 17 (TASK 24) COMPLETE FLASHCARD SET

#### 🔹 CLOSURE FOUNDATIONS

✅ FLASHCARD 1

Front: What is project closure?
Back: Formal process of completing project activities, obtaining acceptance, closing contracts, and archiving information.
Memory Hook: Closure = finish + document.
Trigger Words: “finalize,” “completion”

✅ FLASHCARD 2

Front: What is the FIRST step in closure?
Back: Confirm all project deliverables are completed and accepted.
Memory Hook: No acceptance = no closure.
Trigger Words: “deliverable acceptance,” “final approval”

#### 🔹 DELIVERABLE ACCEPTANCE

❇️ FLASHCARD 3

Front: Who formally accepts final deliverables?
Back: The customer or authorized stakeholder.
Memory Hook: Customer signs off.
Trigger Words: “final acceptance,” “customer approval”

❇️ FLASHCARD 4

Front: What should PM do if deliverables are rejected?
Back: Document defects, revise deliverables, and re-submit for approval.
Memory Hook: Reject = rework + resubmit.
Trigger Words: “defects,” “not accepted”

#### 🔹 ADMINISTRATIVE CLOSURE

❇️ FLASHCARD 5

Front: What is administrative closure?
Back: Documenting results, closing project accounts, updating records, releasing information.
Memory Hook: Paperwork to close.
Trigger Words: “documentation,” “archiving”

❇️ FLASHCARD 6

Front: What should PM ensure before administrative closure?
Back: All documents updated, lessons learned captured, reports completed, baselines finalized.
Memory Hook: Update everything.
Trigger Words: “final documentation,” “completion”

#### 🔹 CONTRACT CLOSURE

❇️ FLASHCARD 7

Front: What is contract closure?
Back: Ensuring all vendor obligations satisfied, invoices settled, claims resolved.
Memory Hook: Close vendor first.
Trigger Words: “procurement closure,” “vendor finalization”

❇️ FLASHCARD 8

Front: What must happen before closing a contract?
Back: Deliverables accepted, financials reconciled, paperwork completed.
Memory Hook: No open items → close contract.
Trigger Words: “vendor acceptance,” “final payment”

#### 🔹 RESOURCE & TEAM RELEASE

❇️ FLASHCARD 9

Front: What is the PM’s responsibility when releasing the team?
Back: Release resources formally and provide performance feedback to functional managers.
Memory Hook: Release + review.
Trigger Words: “resource release,” “feedback”

❇️ FLASHCARD 10

Front: Why is formal release important?
Back: Ensures organizational clarity and prevents double allocation.
Memory Hook: Release = availability.
Trigger Words: “resource planning,” “capacity”

#### 🔹 TRANSITION TO OPERATIONS

❇️ FLASHCARD 11

Front: What is operational transition?
Back: Moving final deliverables into production or business operations.
Memory Hook: From build to run.
Trigger Words: “handover,” “production readiness”

❇️ FLASHCARD 12

Front: What does PM verify before transition to operations?
Back: Training completed, support processes in place, documentation delivered, acceptance confirmed.
Memory Hook: Ready to run.
Trigger Words: “support,” “preparedness”

#### 🔹 KNOWLEDGE TRANSFER IN CLOSURE

❇️ FLASHCARD 13

Front: What should PM do regarding knowledge transfer at closure?
Back: Ensure all training, documentation, and handover activities are complete.
Memory Hook: Complete KT before closure.
Trigger Words: “handover,” “documentation”

❇️ FLASHCARD 14

Front: What should PM do if receiving team is not ready?
Back: Delay closure or adjust timeline until readiness is achieved.
Memory Hook: No readiness = no closure.
Trigger Words: “unprepared,” “transition risk”

#### 🔹 FINAL REPORTING & METRICS

❇️ FLASHCARD 15

Front: What is included in the final project report?
Back: Performance summary (scope, schedule, cost), variances, lessons learned, stakeholder assessment.
Memory Hook: Tell the full story.
Trigger Words: “final report,” “project summary”

❇️ FLASHCARD 16

Front: What is the purpose of variance analysis at closure?
Back: Compare planned vs actual results to evaluate performance.
Memory Hook: Measure results.
Trigger Words: “variance,” “performance evaluation”

#### 🔹 ARCHIVING & RECORD RETENTION

❇️ FLASHCARD 17

Front: What must be archived during closure?
Back: Contracts, plans, logs, deliverables, approvals, performance data, lessons learned.
Memory Hook: Archive the project memory.
Trigger Words: “records,” “repository”

❇️ FLASHCARD 18

Front: Why is archiving important?
Back: Supports audits, future reference, and organizational learning.
Memory Hook: Archive = organizational knowledge.
Trigger Words: “audit,” “historical data”

#### 🔹 STAKEHOLDER COMMUNICATION & SIGN-OFF

❇️ FLASHCARD 19

Front: How should PM communicate project closure?
Back: Announce closure, highlight accomplishments, provide final performance results.
Memory Hook: Communicate the finish.
Trigger Words: “closure message,” “stakeholder update”

❇️ FLASHCARD 20

Front: What should PM do if stakeholder refuses to sign off?
Back: Clarify acceptance criteria, resolve outstanding issues, negotiate expectations.
Memory Hook: Resolve before closure.
Trigger Words: “approval pending,” “disagreement”

#### 🔹 AGILE / HYBRID CLOSURE

❇️ FLASHCARD 21

Front: How is closure handled in Agile?
Back: Review increments, confirm acceptance, update backlog, perform retrospective.
Memory Hook: Close iteration + close release.
Trigger Words: “increment review,” “retro”

❇️ FLASHCARD 22

Front: Who signs off on completion in Agile?
Back: Product Owner accepts completed increments.
Memory Hook: PO = acceptance authority.
Trigger Words: “Done,” “acceptance criteria”

#### 🔹 TROUBLESHOOTING PMI EXAM SCENARIOS

❇️ FLASHCARD 23

Front: What should PM do if closeout activities are skipped due to schedule pressure?
Back: Push back and complete closure—skipping creates future risks.
Memory Hook: Never skip closure steps.
Trigger Words: “rushed closure,” “incomplete”

❇️ FLASHCARD 24

Front: What should PM do if historical data is missing?
Back: Reconstruct data from available sources, interview team, update before archiving.
Memory Hook: Rebuild if missing.
Trigger Words: “incomplete records,” “data gap”

### 📘 DOMAIN III — SECTION 1 (TASK 25) COMPLETE FLASHCARD SET

#### 🔹 COMPLIANCE BASICS

✅ FLASHCARD 1

Front: What is project compliance?
Back: Ensuring the project adheres to laws, regulations, industry standards, and organizational policies.
Memory Hook: Compliance = follow the rules.
Trigger Words: “regulatory,” “policy adherence”

✅ FLASHCARD 2

Front: What is the FIRST step in planning compliance?
Back: Identify all applicable compliance requirements early in the project.
Memory Hook: Identify first, manage second.
Trigger Words: “identify requirements,” “baseline”

#### 🔹 IDENTIFICATION OF REQUIREMENTS

❇️ FLASHCARD 3

Front: What categories of compliance should PM review?
Back: Legal, regulatory, contractual, industry standards, environmental, organizational policies.
Memory Hook: Legal–Regulatory–Contractual–Internal.
Trigger Words: “external rules,” “internal rules”

❇️ FLASHCARD 4

Front: What should PM do when compliance requirements conflict?
Back: Escalate to sponsor and legal/PMO to resolve priority or interpretation.
Memory Hook: Conflicts require authority review.
Trigger Words: “regulatory conflict,” “legal involvement”

#### 🔹 DOCUMENTING COMPLIANCE

❇️ FLASHCARD 5

Front: What tool is used to track compliance?
Back: Compliance management plan or compliance register.
Memory Hook: Track so you don’t miss.
Trigger Words: “policy log,” “compliance plan”

❇️ FLASHCARD 6

Front: What data should be included in a compliance register?
Back: Requirement description, owner, due dates, verification method, status.
Memory Hook: Who + what + when + how verified.
Trigger Words: “tracking,” “owner,” “status”

#### 🔹 EXECUTION OF COMPLIANCE

❇️ FLASHCARD 7

Front: How should PM ensure compliance activities are performed?
Back: Integrate compliance tasks into schedule, monitor regularly, and assign ownership.
Memory Hook: Compliance must be scheduled.
Trigger Words: “integration,” “task assignment”

❇️ FLASHCARD 8

Front: What should PM do when compliance tasks are ignored?
Back: Follow escalation path, reinforce importance, update risk register.
Memory Hook: Non-compliance = risk escalation.
Trigger Words: “non-compliance,” “escalate”

#### 🔹 QUALITY & AUDIT ALIGNMENT

❇️ FLASHCARD 9

Front: How is compliance related to quality?
Back: Compliance ensures outputs meet required standards; quality ensures fitness for use.
Memory Hook: Compliance = required. Quality = desired.
Trigger Words: “standards,” “policy alignment”

❇️ FLASHCARD 10

Front: What should PM do before an audit?
Back: Review documentation, validate evidence, ensure required artifacts are complete.
Memory Hook: Prepare before auditors arrive.
Trigger Words: “audit prep,” “verification”

❇️ FLASHCARD 11

Front: What should PM do when auditors find a compliance gap?
Back: Document findings, perform root cause analysis, create corrective action plan.
Memory Hook: Gap → root cause → correction.
Trigger Words: “nonconformity,” “corrective action”

#### 🔹 RISK & COMPLIANCE

❇️ FLASHCARD 12

Front: How does compliance relate to risk management?
Back: Non-compliance introduces legal, financial, and operational risks.
Memory Hook: Compliance risk = high-impact risk.
Trigger Words: “legal risk,” “penalties”

❇️ FLASHCARD 13

Front: What should PM do if a compliance requirement changes mid-project?
Back: Update plans, adjust schedule/budget, communicate impacts, revise deliverables.
Memory Hook: Change → update plans.
Trigger Words: “regulatory update,” “change control”

#### 🔹 CONTRACTUAL COMPLIANCE

❇️ FLASHCARD 14

Front: What is contractual compliance?
Back: Ensuring project meets obligations defined in vendor or client contracts.
Memory Hook: Honor the contract.
Trigger Words: “SLA,” “contract terms”

❇️ FLASHCARD 15

Front: What should PM do if vendors do not meet compliance requirements?
Back: Document, escalate through procurement, enforce contract terms.
Memory Hook: Escalate through procurement.
Trigger Words: “vendor non-compliance,” “enforcement”

#### 🔹 COMPLIANCE IN AGILE/HYBRID ENVIRONMENTS

❇️ FLASHCARD 16

Front: How is compliance handled in Agile?
Back: Integrated into Definition of Done, sprint reviews, and acceptance criteria.
Memory Hook: DoD includes compliance.
Trigger Words: “DoD,” “iterative compliance”

❇️ FLASHCARD 17

Front: What should PM do when compliance requires heavy documentation in Agile?
Back: Use hybrid approach—maintain docs while delivering iteratively.
Memory Hook: Agile + documentation = hybrid.
Trigger Words: “regulatory burden,” “balance”

#### 🔹 ETHICAL & LEGAL IMPLICATIONS

❇️ FLASHCARD 18

Front: What should PM do when asked to bypass a compliance rule?
Back: Refuse, escalate to sponsor, and ensure adherence to PMI ethics.
Memory Hook: Ethics > pressure.
Trigger Words: “ethics,” “integrity,” “legal risk”

❇️ FLASHCARD 19

Front: What should PM do when compliance requirement is unclear?
Back: Seek clarification from legal, PMO, or compliance experts.
Memory Hook: Don’t assume—verify.
Trigger Words: “interpretation,” “clarification needed”

#### 🔹 TROUBLESHOOTING PMI EXAM SCENARIOS

❇️ FLASHCARD 20

Front: What should PM do if team ignores compliance procedures to save time?
Back: Stop work, correct behavior, reinforce compliance requirements.
Memory Hook: Non-compliance cannot continue.
Trigger Words: “cutting corners,” “urgent correction”

❇️ FLASHCARD 21

Front: What should PM do when compliance documentation is missing?
Back: Recreate documentation using audits, logs, interviews, and available artifacts.
Memory Hook: Rebuild missing docs.
Trigger Words: “missing paperwork,” “reconstruction”

❇️ FLASHCARD 22

Front: What should PM do when stakeholders resist compliance tasks?
Back: Educate on consequences, involve sponsor, align on risks.
Memory Hook: Education + escalation.
Trigger Words: “resistance,” “noncompliance”

### 📘 DOMAIN III — SECTION 2 (TASK 26) COMPLETE FLASHCARD SET

#### 🔹 BENEFITS & VALUE FOUNDATIONS

✅ FLASHCARD 1

Front: What is a project benefit?
Back: A measurable improvement resulting from project outcomes (financial or nonfinancial).
Memory Hook: Benefit = positive outcome.
Trigger Words: “improvement,” “gain,” “value added”

✅ FLASHCARD 2

Front: What is value delivery?
Back: Ensuring project outputs create the intended business value as defined in the business case.
Memory Hook: Deliver value, not just deliverables.
Trigger Words: “business value,” “impact”

#### 🔹 BUSINESS CASE ALIGNMENT

❇️ FLASHCARD 3

Front: What is the business case used for?
Back: Justifying the project based on anticipated benefits, costs, and risks.
Memory Hook: Business case = why we do it.
Trigger Words: “justification,” “ROI,” “strategic alignment”

❇️ FLASHCARD 4

Front: What should PM do when deliverables don’t align with the business case?
Back: Evaluate gaps, escalate to sponsor, and propose corrective actions.
Memory Hook: Misalignment = escalate.
Trigger Words: “off track,” “not aligned”

#### 🔹 BENEFITS REALIZATION PLAN

❇️ FLASHCARD 5

Front: What is a benefits realization plan?
Back: Document that outlines how and when project benefits will be achieved, measured, and sustained.
Memory Hook: Plan how benefits will materialize.
Trigger Words: “tracking value,” “benefits roadmap”

❇️ FLASHCARD 6

Front: Who owns benefits realization?
Back: Typically the sponsor or business owner—not the PM.
Memory Hook: PM tracks; sponsor owns.
Trigger Words: “ownership,” “accountability”

#### 🔹 KPIs & MEASUREMENT

❇️ FLASHCARD 7

Front: What are KPIs?
Back: Quantifiable measures used to evaluate success and progress toward benefits.
Memory Hook: KPIs = metrics of success.
Trigger Words: “performance indicators,” “measurement”

❇️ FLASHCARD 8

Front: What should PM do if KPIs indicate benefits are not being met?
Back: Analyze root cause, adjust plans, coordinate with sponsor/team.
Memory Hook: Poor KPI = corrective action.
Trigger Words: “underperformance,” “metrics issue”

#### 🔹 BENEFIT TRACKING & REPORTING

❇️ FLASHCARD 9

Front: How should PM track benefits?
Back: Monitor KPI trends, compare actual vs expected, report variances.
Memory Hook: Track trends, not just snapshots.
Trigger Words: “variance,” “progress tracking”

❇️ FLASHCARD 10

Front: When should benefits be reviewed?
Back: Throughout the project lifecycle and after project completion.
Memory Hook: Benefits extend beyond delivery.
Trigger Words: “post-implementation,” “ongoing review”

#### 🔹 VALUE SUSTAINMENT

❇️ FLASHCARD 11

Front: What is required to sustain benefits?
Back: Proper handover, training, operational processes, funding, and maintenance.
Memory Hook: Sustain value after delivery.
Trigger Words: “operations,” “maintenance”

❇️ FLASHCARD 12

Front: What should PM do if benefits fade after project ends?
Back: Document root causes, capture lessons learned, and recommend improvements.
Memory Hook: Capture lessons for next time.
Trigger Words: “benefits decay,” “long-term issues”

#### 🔹 STAKEHOLDER ALIGNMENT

❇️ FLASHCARD 13

Front: How should PM ensure stakeholders understand value delivery?
Back: Communicate benefits status, KPI metrics, risks, and expected outcomes.
Memory Hook: Value must be visible.
Trigger Words: “communication,” “updates”

❇️ FLASHCARD 14

Front: What should PM do if stakeholders disagree on expected benefits?
Back: Align using business case, charter, and originally defined success criteria.
Memory Hook: Use documented sources to align.
Trigger Words: “misalignment,” “conflict”

#### 🔹 AGILE/HYBRID VALUE DELIVERY

❇️ FLASHCARD 15

Front: How is value delivered in Agile?
Back: In small increments, enabling early and continuous value realization.
Memory Hook: Value early and often.
Trigger Words: “incremental,” “iterative delivery”

❇️ FLASHCARD 16

Front: Who is responsible for maximizing value in Agile?
Back: The Product Owner.
Memory Hook: PO = value steward.
Trigger Words: “backlog prioritization,” “value maximization”

❇️ FLASHCARD 17

Front: How does hybrid deliver value?
Back: Predictive components define high-level benefits; Agile increments refine and validate them.
Memory Hook: Hybrid = define + validate.
Trigger Words: “mixed approach,” “value feedback”

#### 🔹 ROI & FINANCIAL BENEFITS

❇️ FLASHCARD 18

Front: What is ROI used for?
Back: Measuring financial return compared to project investment.
Memory Hook: ROI = financial value.
Trigger Words: “investment return,” “financial measure”

❇️ FLASHCARD 19

Front: What should PM do if project cost increases reduce ROI?
Back: Assess impact, revise business case, escalate to sponsor.
Memory Hook: Lower ROI = re-evaluate.
Trigger Words: “cost overrun,” “impact to value”

#### 🔹 BENEFITS & ORGANIZATIONAL STRATEGY

❇️ FLASHCARD 20

Front: How do projects support strategic goals?
Back: By delivering benefits aligned with organizational objectives and growth priorities.
Memory Hook: Projects drive strategy.
Trigger Words: “strategic alignment,” “organizational goals”

❇️ FLASHCARD 21

Front: What should PM do when strategy changes mid-project?
Back: Review alignment, evaluate impact, recommend adjustments to scope/time/cost.
Memory Hook: Strategy change = project adjustment.
Trigger Words: “pivot,” “realignment”

#### 🔹 TROUBLESHOOTING PMI EXAM SCENARIOS

❇️ FLASHCARD 22

Front: What should PM do when project produces deliverables but no business value?
Back: Reassess KPIs, business case alignment, and stakeholder expectations.
Memory Hook: Deliverables ≠ value.
Trigger Words: “misaligned output,” “no benefit realized”

❇️ FLASHCARD 23

Front: What should PM do when benefits are delayed beyond project closure?
Back: Document benefit ownership and establish post-implementation review plan.
Memory Hook: Benefits may occur later.
Trigger Words: “future benefits,” “handover”

❇️ FLASHCARD 24

Front: What should PM do when data is insufficient to measure benefits?
Back: Collect additional data, refine measurement plan, improve KPI definitions.
Memory Hook: Measure correctly or adjust.
Trigger Words: “data gaps,” “measurement issues”

### 📘 DOMAIN III — SECTION 3 (TASK 27) COMPLETE FLASHCARD SET

#### 🔹 EXTERNAL ENVIRONMENT FOUNDATIONS

✅ FLASHCARD 1

Front: What is the external business environment?
Back: Factors outside the project that influence success (legal, market, economic, technological, social).
Memory Hook: Outside forces → inside impact.
Trigger Words: “external factors,” “outside control”

✅ FLASHCARD 2

Front: What is the PM’s first step when external changes occur?
Back: Assess impact on scope, schedule, cost, risk, resources, and deliverables.
Memory Hook: Assess before reacting.
Trigger Words: “impact analysis,” “external shift”

#### 🔹 TYPES OF EXTERNAL CHANGES

❇️ FLASHCARD 3

Front: What are examples of external changes?
Back: Regulatory updates, market fluctuations, competitor actions, new technologies, supply chain issues.
Memory Hook: REMS: Regulations, Economy, Market, Supply.
Trigger Words: “industry,” “market change”

❇️ FLASHCARD 4

Front: How can economic changes affect your project?
Back: Budget cuts, inflation, funding changes, resource shortages.
Memory Hook: Economy affects cost + resources.
Trigger Words: “budget impact,” “economic shift”

#### 🔹 REGULATORY & LEGAL CHANGES

❇️ FLASHCARD 5

Front: What should PM do if new regulations impact the project?
Back: Update plans, communicate changes, adjust scope/schedule/cost, escalate to sponsor.
Memory Hook: Law change → plan change.
Trigger Words: “regulation,” “compliance”

❇️ FLASHCARD 6

Front: What should PM do if team is unaware of regulatory changes?
Back: Educate team, update documentation, align compliance tasks.
Memory Hook: Educate before executing.
Trigger Words: “compliance gap,” “training needed”

#### 🔹 ORGANIZATIONAL CHANGES

❇️ FLASHCARD 7

Front: What organizational changes can impact a project?
Back: Mergers, acquisitions, leadership turnover, restructuring, strategic pivots.
Memory Hook: Org change = alignment reset.
Trigger Words: “leadership change,” “merger”

❇️ FLASHCARD 8

Front: What should PM do when leadership changes?
Back: Revalidate project goals and confirm continued alignment/support.
Memory Hook: New leadership = new priorities.
Trigger Words: “leadership shift,” “reconfirmation”

#### 🔹 MARKET & TECHNOLOGY SHIFTS

❇️ FLASHCARD 9

Front: How should PM respond to new competing technologies?
Back: Analyze whether to incorporate updates, adjust scope, or reevaluate business case.
Memory Hook: Tech changes = revisit value.
Trigger Words: “technology disruption,” “innovation”

❇️ FLASHCARD 10

Front: What should PM do when market demand drops?
Back: Evaluate project viability, discuss with sponsor, adjust business case.
Memory Hook: Market drop = reassess project viability.
Trigger Words: “market shift,” “demand decrease”

#### 🔹 SUPPLY CHAIN & VENDOR IMPACTS

❇️ FLASHCARD 11

Front: What should PM do if vendor delays occur?
Back: Identify impact, update schedule, escalate if severe, explore alternative sources.
Memory Hook: Vendor delay = risk response.
Trigger Words: “supplier issue,” “delay”

❇️ FLASHCARD 12

Front: How should PM respond to global supply chain disruptions?
Back: Reassess availability, rebaseline schedule, adjust procurement plans.
Memory Hook: Global disruption = replan.
Trigger Words: “supply chain,” “procuring”

#### 🔹 IMPACT ASSESSMENT & ADAPTATION

❇️ FLASHCARD 13

Front: What should PM evaluate when external changes occur?
Back: Impact on scope, schedule, cost, risk, quality, resources, stakeholders.
Memory Hook: SSCRRQ — Scope, Schedule, Cost, Risk, Quality.
Trigger Words: “impact mapping,” “dependencies”

❇️ FLASHCARD 14

Front: What is the PM’s next step after assessing impact?
Back: Update risk register, create response strategies, modify plans accordingly.
Memory Hook: Assess → update risks.
Trigger Words: “risk adjustment,” “mitigation”

#### 🔹 STAKEHOLDER COMMUNICATION

❇️ FLASHCARD 15

Front: How should PM communicate external changes?
Back: Share impacts, recommended updates, risks, and revised expectations.
Memory Hook: Transparency is critical.
Trigger Words: “communication,” “status change”

❇️ FLASHCARD 16

Front: What should PM do if stakeholders disagree on how to respond?
Back: Facilitate discussion, use data, escalate if alignment cannot be reached.
Memory Hook: Data resolves debate.
Trigger Words: “conflict,” “misalignment”

#### 🔹 ADAPTATION IN AGILE/HYBRID

❇️ FLASHCARD 17

Front: How does Agile respond to external changes?
Back: Through backlog reprioritization, iterative planning, and quick adaptation.
Memory Hook: Agile adapts fast.
Trigger Words: “backlog,” “iteration”

❇️ FLASHCARD 18

Front: What should PM do in hybrid when external changes occur?
Back: Adjust predictive components while flexibly reprioritizing Agile elements.
Memory Hook: Hybrid = structured adaptation.
Trigger Words: “mixed approach,” “dual planning”

#### 🔹 TROUBLESHOOTING PMI EXAM LOGIC

❇️ FLASHCARD 19

Front: What should PM do when external changes require altering project scope?
Back: Follow formal change control, analyze impacts, obtain approvals.
Memory Hook: Change = formal process.
Trigger Words: “change control,” “scope impact”

❇️ FLASHCARD 20

Front: What should PM do if external changes invalidate original requirements?
Back: Reassess business case, halt work if necessary, coordinate with sponsor.
Memory Hook: Invalid requirements = stop + reassess.
Trigger Words: “requirements shift,” “reanalysis”

❇️ FLASHCARD 21

Front: What should PM do when external risks suddenly increase?
Back: Update risk responses and escalate high-impact risks.
Memory Hook: New risk = update & escalate.
Trigger Words: “risk spike,” “mitigation update”