## Sheet1
Here is the revised transition plan with a column explaining where AI can help. AI can accelerate analysis, drafting, and development; business and technical owners should validate its outputs before approval or deployment.
Step | What needs to happen | Key deliverable | Where AI can help | Acceptance criteria
1. Assess the current application | Inventory screens, workflows, business rules, reports, integrations, data, user roles, and known problems. Identify business and technical owners. | Current-state assessment | Summarize existing documentation and code, draft process maps, extract business rules, and identify gaps or questions for stakeholders. | All in-scope screens, workflows, business rules, reports, integrations, and data sources are documented. User roles and application dependencies are identified. Business and technical owners validate the assessment.
2. Define the scope and success measures | Decide which capabilities to retain, improve, or retire. Define the first release and measurable outcomes. | Approved requirements and release scope | Turn stakeholder notes into requirements, user stories, and acceptance criteria. Flag duplicates, conflicting requirements, and unclear scope. | Every in-scope requirement has a unique ID, priority, owner, and testable acceptance criteria. First-release scope and exclusions are approved. Success measures have documented baselines and targets.
3. Confirm Power Apps suitability | Evaluate volumes, performance, complex processing, offline needs, integrations, security, and licensing costs. Prototype high-risk functionality. | Feasibility decision and proof of concept | Create assessment checklists, identify potential constraints, and suggest prototype scenarios. Validate platform capabilities and licensing against current Microsoft guidance. | A proof of concept demonstrates the highest-risk business scenarios using representative data volumes. Performance meets agreed targets. Integration, security, licensing, and platform constraints are assessed, with no unresolved feasibility blockers.
4. Select the application architecture | Choose canvas, model-driven, or a combination. Determine needs for Power Pages and Power Automate. | Target solution design | Draft architecture options, compare tradeoffs, and propose initial data models and workflow designs for technical review. | The application type, data platform, integrations, and automation approach are documented and approved. The design addresses required user journeys, access needs, error handling, and supportability.
5. Plan the data and integrations | Decide which data stays or moves. Map tables, relationships, attachments, history, and interfaces. Define reconciliation rules. | Data migration and integration plan | Suggest field mappings, identify possible data-quality issues, and draft transformation logic, integration specifications, and reconciliation queries. | All in-scope data fields and relationships have approved mappings. A trial migration meets agreed record-count and accuracy thresholds. Required attachments and history are preserved. Integrations pass normal, failure, and recovery scenarios without unexplained data loss or duplication.
6. Establish environments and security | Set up development, test, and production environments. Configure access, security roles, connector policies, and deployment controls. | Ready environments and approved access model | Draft role-access matrices, environment checklists, and deployment documentation. Flag potential permission gaps for security review. | Development, test, and production environments are configured. Tests confirm users can perform authorized actions and cannot access restricted data or functions. Connector policies are approved. A deployment rehearsal succeeds using environment-specific configuration.
7. Build the application incrementally | Develop screens, forms, rules, approvals, notifications, integrations, and reports. Demonstrate functionality regularly. | Working application releases | Assist with Power Fx formulas, workflow logic, screen designs, and technical documentation. Explain errors and suggest fixes that developers test. | All first-release requirements are implemented and traceable to working functionality. Business rules, approvals, notifications, and reports behave as specified. Error messages are actionable. Product owners accept completed features.
8. Test and obtain business acceptance | Validate functionality, permissions, integrations, data accuracy, performance, accessibility, and critical business scenarios. Conduct UAT. | Test results and UAT signoff | Generate test cases from requirements, suggest edge cases, create synthetic test data, and summarize defects and coverage gaps. | All critical business scenarios pass. No open critical or high-severity defects remain, unless an authorized exception is documented. Performance and accessibility meet agreed targets. Business representatives complete UAT and approve release readiness.
9. Prepare and execute cutover | Train users, rehearse migration, plan any outage, load final changes, validate production, and establish rollback criteria. | Approved cutover plan and production launch | Draft cutover runbooks, training materials, communications, and rollback checklists. Analyze rehearsal results to identify missed dependencies. | The cutover rehearsal finishes within the planned window. Final data reconciliation passes. User access, training, support coverage, and communications are ready. Rollback triggers and responsibilities are documented and rehearsed. Production smoke tests pass before release to users.
10. Transition to support and retire the old system | Assign support ownership, provide documentation, monitor adoption and failures, complete hypercare, and retire the legacy application after acceptance. | Operational handoff and retirement approval | Draft support guides and FAQs, summarize recurring incidents, analyze adoption feedback, and suggest improvements for the backlog. | The support owner accepts the runbook, access, monitoring, and escalation responsibilities. The support team demonstrates that it can resolve representative incidents independently. The application meets agreed stability targets for [X days]. Required legacy records are archived and retrievable before retirement approval.
The strongest starting opportunities are requirements drafting, documentation analysis, development assistance, and test-case generation. These produce tangible outputs that the team can review before using them.
For AI-assisted work, add these acceptance criteria across the phases:
Area | Acceptance criteria | Column1 | Column2
Requirements and documentation | A designated owner reviews AI-generated content against source material. Unsupported assumptions are resolved or explicitly recorded before approval.
Formulas, code, and workflows | AI-generated components pass the same review, security checks, and functional tests as other components. No untested generated logic is deployed.
Migration and data mapping | Proposed mappings and transformations are validated using representative records and reconciliation results before production use.
Testing | Test cases trace to approved requirements. Expected results are independently verified, and actual execution evidence supports pass/fail decisions.
Data handling | Information supplied to AI tools complies with the organization’s approved data-handling rules.
Approval and accountability | Named business or technical owners approve deliverables and release decisions, including those prepared with AI assistance.
A useful format for individual application requirements is Given / When / Then:
Given an authorized approver has a request awaiting review,
When they approve the request,
Then its status changes to “Approved,” the approver and timestamp are recorded, and the requester receives a notification within [X minutes].