## Sheet1
Project Phase | Checklist Item | Completed | Start Date | End Date
Phase 1: Define Objectives and Scope | Identify the business use case (e.g., alpha generation, anomaly detection, process automation) | FALSE
Phase 1: Define Objectives and Scope | Engage with key stakeholders (portfolio managers, traders, quants, compliance) | FALSE
Phase 1: Define Objectives and Scope | Define success criteria and KPIs (accuracy, time savings, ROI, risk reduction) | FALSE
Phase 1: Define Objectives and Scope | Determine budget and resource allocation | FALSE
Phase 2: Data Readiness | Assess data availability and quality (market data, internal data, third-party feeds) | FALSE
Phase 2: Data Readiness | Ensure clean, labeled, and structured datasets | FALSE
Phase 2: Data Readiness | Confirm data permissions and compliance (e.g., GDPR, SEC, internal policies) | FALSE
Phase 2: Data Readiness | Plan for real-time vs batch processing needs | FALSE
Phase 2: Data Readiness | Identify data owners and stewards | FALSE
Phase 3: Model Development | Partner with quant/data science teams for model selection and design | FALSE
Phase 3: Model Development | Agree on training, validation, and testing protocols | FALSE
Phase 3: Model Development | Build an experiment tracking process (versioning, reproducibility, outcomes) | FALSE
Phase 3: Model Development | Align development schedule with sprints or milestones | FALSE
Phase 3: Model Development | Conduct bias checks and explainability reviews | FALSE
Phase 4: Technology & Integration | Define integration points with OMS/EMS, risk systems, or BI tools | FALSE
Phase 4: Technology & Integration | Review compute and infrastructure requirements (on-prem vs cloud) | FALSE
Phase 4: Technology & Integration | Set up APIs or endpoints for model output access | FALSE
Phase 4: Technology & Integration | Conduct performance and latency testing | FALSE
Phase 4: Technology & Integration | Collaborate with DevOps/IT for deployment pipeline setup | FALSE
Phase 5: Risk, Compliance & Audit | Schedule review with compliance/legal teams | FALSE
Phase 5: Risk, Compliance & Audit | Ensure model explainability and audit trails | FALSE
Phase 5: Risk, Compliance & Audit | Perform cybersecurity and penetration testing | FALSE
Phase 5: Risk, Compliance & Audit | Document and store model logic, data lineage, and decision processes | FALSE
Phase 5: Risk, Compliance & Audit | Confirm adherence to SOC 1/SOC 2, SEC, MiFID II if applicable | FALSE
Phase 6: Testing and Validation | Conduct UAT (User Acceptance Testing) with business stakeholders | FALSE
Phase 6: Testing and Validation | Validate model outputs with real-world scenarios | FALSE
Phase 6: Testing and Validation | Include human-in-the-loop validation steps as needed | FALSE
Phase 6: Testing and Validation | Address any drift, anomalies, or retraining requirements | FALSE
Phase 6: Testing and Validation | Finalize go/no-go for deployment | FALSE
Phase 7: Launch and Change Management | Prepare training materials, SOPs, and documentation | FALSE
Phase 7: Launch and Change Management | Communicate clearly to all impacted users and teams | FALSE
Phase 7: Launch and Change Management | Establish support and escalation procedures | FALSE
Phase 7: Launch and Change Management | Conduct change readiness and adoption assessments | FALSE
Phase 7: Launch and Change Management | Monitor user feedback and model performance in production | FALSE
Phase 8: Ongoing Monitoring and Iteration | Set up dashboards for KPIs, alerts, and performance tracking | FALSE
Phase 8: Ongoing Monitoring and Iteration | Schedule regular model retraining and data refreshes | FALSE
Phase 8: Ongoing Monitoring and Iteration | Monitor for regulatory updates or business shifts requiring adjustments | FALSE
Phase 8: Ongoing Monitoring and Iteration | Hold post-launch retrospectives and document lessons learned | FALSE
Phase 8: Ongoing Monitoring and Iteration | Plan next phase or scale-out if successful | FALSE